## data
id | kind | date | project_en | project_ar | licensee_en | licensee_ar | state_company_en | state_company_ar | province | land_en | land_ar | value | currency | terms_en | terms_ar | follow_up_en | follow_up_ar | official_findings_en | official_findings_ar | quote | source_urls
IND-001 | licence or land | 2021-12-27 | Karbala Industrial City: development contract No. 4 of 2021 with the Industrial Cities Authority (city for oil and petrochemical industries) |  | Al-Yusra Co. for General Contracting, Energy Projects and Industrial Development (LLC, Iraqi); called Al-Yusra Industrial by Iraq Business News | شركة اليسرة للمقاولات العامة ومشاريع الطاقة والتطوير الصناعي محدودة المسؤولية |  |  | Karbala | 5,300 dunums allocated by the governorate through its land allocation committee, then a development contract with the developer (Industrial Cities Authority to INA, 13 May 2026) | [5 empty] | Minister Manhal al-Khabbaz announced on 30 Aug 2021 that the approvals of the tourism and antiquities, agriculture and water resources authorities had been obtained for a 5,300-dunum industrial city for oil and petrochemical industries. PM Mohammed Shia al-Sudani inaugurated the construction of four chemical and industrial projects in the city in Aug 2024. On 19 Apr 2025 Minister Khaled Battal said infrastructure had passed 60 percent, power supply for every plant is the developer's task, and the company had begun to surround the city with 16 km of concrete fence. Addendum No. 2 of 21 Apr 2025 changed the implementation period from 3 to 6 years and the development period from 40 to 45 years. On 13 May 2026 the Authority's head, Anas Hashim Abdul-Majeed, told INA that overall completion was about 67 percent and infrastructure about 80 percent, and called it the first contract given to the private sector to build an industrial city; an Authority official said no money came from the state budget or the ministry. |  | FBSA report 20706 of 12 Aug 2025 found no convincing reasons for addendum No. 2 or for a clause sending 8 Authority staff to Turkey for seven days, and recommended an investigation. The FBSA text does not name the city; the link to Karbala rests on Iraq Business News, citing the ministry, naming Al-Yusra Industrial as the developer (our inference, tier B). On 11 May 2026 MP Zahraa Luqman al-Saadi (Badr) said in a television interview that USD 800 million had been stolen in a fictitious Ministry of Industry project in Karbala; she named no company. The ministry denied it, said it has no industrial complex in Karbala, only an industrial city of 5,300 dunums being built by the private sector with no financial contribution from the state, and said it would take legal action against her. Status of Al-Yusra: not charged as of the date of writing (as of 2026-05-13). |  | تمت احالة عقد إنشاء و تطوير مدينة صناعية في كربلاء بمساحة خمسة آلاف وثلاث مئة دونم الى إحدى شركات القطاع الخاص ¦ The agreements were signed between Al-Yusra Industrial, the developer of Karbala Industrial City, and China's SEPCO | ["https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026651_4169813074291734.pdf#page=303", "https://www.iraq-businessnews.com/2025/04/20/chinese-firm-signs-mous-for-iraq-petrochemical-projects/", "https://ina.iq/ar/local/263081-.html", "https://964media.com/680232/", "https://www.economy-news.net/content.php?id=54601", "https://www.non14.net/139585", "https://www.iraq-businessnews.com/2024/08/20/iraq-launches-major-industrial-projects-in-karbala-industrial-city/"]
IND-002 | licence or land | 2025-04-19 | Karbala Industrial City: memorandums of understanding for four petrochemical plants, infrastructure, and operation and maintenance, signed with the city's developer |  | SEPCO (SEPCOIII Electric Power Construction Corporation, Shandong Electric Power Construction), named by Economy News as Power China; partner of Al-Yusra Industrial | شركة Power China الصينية |  |  | Karbala | Inside the 5,300-dunum Karbala Industrial City | [5 empty] | In Aug 2024 PM al-Sudani inaugurated construction of four projects in the city: an industrial gases plant (1,000 t a day), a white oils plant (1,000 m3 a day), an organic solvents plant (1,000 m3 a day) and a vacuum distillation plant (2,500 t a day). Whether the 2025 memorandums cover the same four plants is not stated. Minister Khaled Battal said on 19 Apr 2025 that he had discussed obstacles with the developer and its Chinese partner, chiefly electricity supply. |  | None found. Status: not charged as of the date of writing (as of 2025-04-20). |  | وقعت مذكرات تفاهم لانشاء اربعة مصانع في صناعات البتروكيمياوية وتحدثنا مع الشركة المنفذة ومع الشريك الصيني للشركة المنفذة | ["https://www.iraq-businessnews.com/2025/04/20/chinese-firm-signs-mous-for-iraq-petrochemical-projects/", "https://www.economy-news.net/content.php?id=54601", "https://www.iraq-businessnews.com/2024/08/20/iraq-launches-major-industrial-projects-in-karbala-industrial-city/"]
IND-003 | licence or land | 2025-03-22 | Green Mountain (Jabal al-Akhdar) Industrial City for iron, steel and construction materials, Basra: contract signed with the General Company for Iron and Steel; Industrial Cities Authority to issue the development and management licence |  | Tsingshan Holding Group (China) | مجموعة تشينغشان القابضة الصينية (شركة تسنك شان) |  |  | Basra | On land of the General Company for Iron and Steel. Areas as published: 1,800 dunums (ministry at signing, 22 Mar 2025); 2,000 dunums (ministry, May 2025); 3,000 dunums with a 500 m waterfront on Khor al-Zubair (PM's office, 14 May 2025). A Cabinet decision of 15 Oct 2024 let the company partner with a developer on plot 9/17, district 44 Hila (industrial class). |  | 2,000,000,000 | USD |  |  | PM al-Sudani received the company's head, Zhang Jiming, on 30 Nov 2023 (Shafaq writes the company as شانغ شين), and his office said the company would build an industrial city in Basra to make iron from sponge iron. The Supreme Committee for Investment and Reconstruction approved an iron and steel industrial city in partnership with the General Company for Iron and Steel on 8 May 2024. Minister Khaled Battal discussed contracting procedures with Tsingshan on 9 Sep 2024. On 15 Oct 2024 the Cabinet authorised the company to enter a partnership with a developer. The contract was signed on 22 Mar 2025, valued at USD 2 billion by the ministry; Tsingshan's executive director, named by 964 only as Liu, gave the cost as 2 million dollars, which conflicts with the ministry's figure. PM al-Sudani launched works on 14 May 2025: about 20 plants (steel, casting, rolling, pipes, wire, aluminium alloys, ceramics, doors, building materials) and a 1,000 MW power station. That the Oct 2024 plot is the Tsingshan site is our inference (tier B); the Cabinet text does not name the developer. |  | None found. Status of Tsingshan: not charged as of the date of writing (as of 2025-05-16). |  | توقيع عقد لإنشاء المدينة الصناعية في البصرة، التي تمتد على مساحة 1800 دونم، بكلفة ملياري دولار، مع شركة تسنك شان | ["https://964media.com/529281/", "https://964media.com/551119/", "https://964media.com/456396/", "https://www.alsumaria.tv/news/localnews/499504/%D8%B4%D8%B1%D9%83%D8%A9-%D8%B5%D9%8A%D9%86%D9%8A%D8%A9-%D8%AA%D8%AA%D9%88%D9%84%D9%89-%D9%85%D8%B3%D8%A4%D9%88%D9%84%D9%8A%D8%A9-%D8%AA%D8%B7%D9%88%D9%8A%D8%B1-%D9%85%D8%AF%D9%8A%D9%86%D8%A9-%D8%A7%D9%84%D8%B5%D9%84%D8%A8-%D8%A8%D8%A7%D9%84%D8%A8%D8%B5%D8%B1%D8%A9-%D8%AA%D9%88%D8%AC%D9%8A%D9%87%D8%A7%D8%AA-%D8%B1%D8%B3%D9%85%D9%8A%D8%A9", "https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D9%85%D9%83%D8%AA%D8%A8-%D8%A7%D9%84%D8%B3%D9%88%D8%AF%D8%A7%D9%86%D9%8A-%D8%B4%D8%B1%D9%83%D8%A9-%D8%B5%D9%8A%D9%86%D9%8A%D8%A9-%D8%B3%D8%AA%D9%82%D9%88%D9%85-%D8%A8-%D9%86%D8%B4%D8%A7-%D9%85%D8%AF%D9%8A%D9%86%D8%A9-%D8%B5%D9%86%D8%A7%D8%B9%D9%8A%D8%A9-%D9%85%D8%AA%D8%B7%D9%88%D8%B1%D8%A9-%D9%81%D9%8A-%D8%A7%D9%84%D8%A8%D8%B5%D8%B1%D8%A9", "https://www.iraq-businessnews.com/2025/03/25/new-iraq-china-contracts-for-sponge-iron-plant-and-2bn-industrial-city/", "https://www.iraq-businessnews.com/2025/05/16/iraq-and-china-launch-2bn-industrial-city-in-basra/"]
IND-004 | licence or land | 2025-03-22 | Sponge iron plant, capacity 1 million tonnes a year, in partnership with the General Company for Iron and Steel; Minister Khaled Battal said the industrial city signed the same day includes the sponge iron plant |  | Al-Qaim United Company | شركة القائم المتحدة |  |  | Basra | Within the Basra steel industrial city on General Company for Iron and Steel land, per the minister; plant area not given | [5 empty] | On 5 Feb 2026 the Industrial Coordination Council, chaired by PM al-Sudani, approved the use of specialised berths 10 and 11 at Khor al-Zubair port to run the sponge iron plant after its rehabilitation, for its export needs in trial and then commercial operation. |  | None found. Status: not charged as of the date of writing (as of 2026-02-05). |  | عقد إنشاء مصنع الحديد الإسفنجي، بطاقة مليون طن سنوياً، الذي سيتم تنفيذه بالشراكة بين الشركة العامة للحديد والصلب وشركة القائم المتحدة | ["https://964media.com/529281/", "https://964media.com/648842/", "https://www.iraq-businessnews.com/2025/03/25/new-iraq-china-contracts-for-sponge-iron-plant-and-2bn-industrial-city/"]
IND-005 | licence or land | 2026-05-24 | Basra Economic City, an industrial city in Khor al-Zubair (investment licence for 40 years) |  | Not named; 964 describes the developer as a company specialised in iron, steel and industrial investment. Whether this is the Tsingshan project is not stated. |  |  |  | Basra | 904 dunums in the investment licence, on land owned by the Ministry of Finance; farmers say clearance reached about 1,371 dunums |  | 100,000,000 (more than) | USD |  |  | The Zubair district head, Abbas Maher, said Khor al-Zubair was set aside for an integrated industrial project; work on it began in 2007, but the actual start was delayed to Sep 2025, after a developer was contracted. Farmers said more than 40 farms with palm and sidr trees were bulldozed and power lines cut; 20 protesters were arrested on charges that included attempted murder and extortion of the investor and were released on bail after a month (farmers' account). On 14 Jun 2026 farmers in Khwesat said they had still received no compensation. |  | No official finding. The district head said every holder of a formal agricultural contract would be compensated by the investors. The claim that clearance exceeded the licensed area is the farmers' account (tier D). Licensee status: not named. |  | وأعمال التجريف تجاوزت حدود المساحة المثبتة في إجازة الاستثمار البالغة (904) دونمات، لتصل إلى نحو 1371 دونماً | ["https://964media.com/683479/", "https://964media.com/689834/"]
IND-006 | licence or land | 2021-02-05 | Basra Industrial City of the Industrial Cities Authority (plot 30, district 43 Arkali, Khor al-Zubair): 69 serviced plots of 1,200 m2 for small and medium industry |  | General Company for Designs and Project Implementation (state contractor, building the city in phases); General Company for Electrical Industries (24 MW power station). Plot lessees not named. | الشركة العامة للتصاميم وتنفيذ المشاريع (سابقاً)؛ الشركة العامة للصناعات الكهربائية (محطة الكهرباء) |  |  | Basra | 174 dunums, with 95 dunums being added | [5 empty] | Minister Manhal al-Khabbaz said on 5 Feb 2021 that the Basra industrial city was 70 percent complete. The Authority's head visited the site in Mar 2025 to review actual completion, and on 20 Apr 2026 attended a meeting at Basra governorate on simplifying procedures for industrial cities. No list of plot lessees was found. |  | None found for this city. Status of the named state companies: not charged as of the date of writing. |  | تم التعاقد مع الشركة العامة للتصاميم وتنفيذ المشاريع (سابقاً) لغرض تنفيذ المدينة الصناعية وبشكل مراحل | ["https://cities.industry.gov.iq/tenders/details/9", "https://www.alsumaria.tv/news/%D8%A7%D9%82%D8%AA%D8%B5%D8%A7%D8%AF/371740/%D8%A2%D8%AE%D8%B1-%D8%AA%D9%81%D8%A7%D8%B5%D9%8A%D9%84-%D8%A7%D9%84%D9%85%D8%AF%D9%86-%D8%A7%D9%84%D8%B5%D9%86%D8%A7%D8%B9%D9%8A%D8%A9-%D9%81%D9%8A-%D8%A7%D9%84%D8%B9%D8%B1%D8%A7%D9%82", "https://cities.industry.gov.iq/news/details/65", "https://cities.industry.gov.iq/news/details/71"]
IND-007 | licence or land | 2022-11-30 | Najaf Industrial City, Bahr al-Najaf depression, designed as environmentally friendly; developer and implementer |  | Al-Diyar Al-Iraqia (Al-Diyar Al-Iraqia For Investments Company) | شركة الديار العراقية المنفذة للمدن الصناعية |  |  | Najaf | 6,000 dunums in the Bahr al-Najaf depression; phase one on 1,200 dunums (minister, 19 Apr 2025) | [5 empty] | Foundation stone laid on 30 Nov 2022 in the presence of Minister Khaled Battal; the company's manager was quoted by 964 as Salwan Dawood. On 20 Feb 2025 the minister said a committee would set compensation for farmers holding title deeds and that the investors would pay it. On 19 Apr 2025 he said phase one was done on 1,200 dunums, some plants had signed contracts, the developer would build a 35 MW solar plant, and completion would take 8 years. In Dec 2023 PM al-Sudani commended a deal in which Al-Diyar acquired 49 percent of the Iraq investments of Saudi Northern Region Cement Company (NRCC) for USD 43.953 million; BNN Breaking, cited by Iraq Business News, named the company's director as Salman Daoud Salman and placed the 6,000-dunum hub in Najaf. The two spellings of the manager's name differ. |  | None found. Status of Al-Diyar: not charged as of the date of writing (as of 2025-04-19). |  | سلوان داوود مدير شركة الديار العراقية المنفذة للمدن الصناعية قال لـشبكة 964، إن “المدينة الصناعية تضم معامل للمشروبات الغازية والمواد الطبية والإنشائية” | ["https://964media.com/21949/", "https://964media.com/540776/", "https://964media.com/516182/", "https://www.iraq-businessnews.com/2023/12/14/iraqi-saudi-firms-sign-44m-cement-partnership/", "https://www.iraq-businessnews.com/2025/05/05/ifc-to-help-iraq-develop-industrial-cities/"]
IND-008 | licence or land | 2024-05-23 | Flat (float) glass plant in Najaf Industrial City, 800 tonnes a day; the first project of the government's sovereign guarantees initiative for the private sector |  | Al Rida Investment (named by HORN Glass Industries AG as its client) |  |  |  | Najaf | Inside Najaf Industrial City; plot area not given |  | 110,000,000 | EUR |  |  | PM al-Sudani launched works on 23 May 2024. On 5 Jun 2024 the Trade Bank of Iraq signed an authorisation letter with Commerzbank and AKA Bank to finance the plant with EUR 110 million under the sovereign guarantees initiative. On 6 Jul 2026 HORN Glass Industries AG said it had signed with Al Rida Investment to build the plant; equipment delivery is planned for 2027 and commissioning for 2028. |  | None found. Status: not charged as of the date of writing (as of 2026-07-06). No Arabic source naming the project company was found. That Al Rida's Najaf plant (800 t a day, financed through Commerzbank and AKA) is the plant launched in Najaf Industrial City in May 2024 is our inference from matching capacity and lenders (tier B). |  | German firm HORN Glass Industries AG, the has signed a contract with Al Rida Investment to build a new float glass plant in Najaf, with a production capacity of 800 tonnes per day. | ["https://964media.com/374130/", "https://964media.com/382166/", "https://www.iraq-businessnews.com/2026/07/06/german-firm-to-build-float-glass-plant-in-najaf/", "https://www.iraq-businessnews.com/2024/06/07/german-support-for-new-glass-factory-in-najaf/"]
IND-009 | licence or land | 2026-06-10 | Dhi Qar Industrial City (Ur sub-district, Nasiriyah): lease of serviced and unserviced industrial plots |  | Industrialists not named. Projects listed by the Authority: an industrial oil recycling plant, an industrial gases plant, tyre and paper waste recycling plants, food and pharmaceutical plants. |  |  |  | Dhi Qar | 2,000 dunums, district 48 Sakhriya East (plots 5, 7, 8, 9, 11, 21, 24, 47, 50, 51, 59 and abandoned plot 188); phase one 200 dunums with 105 serviced plots of 1,250 m2. 278 plots leased in all, serviced and unserviced (Authority, Jun 2026). |  | 750,000 | IQD a month per 1,250 m2 plot (rent in the Authority's investment opportunity file) |  |  | The opportunity file put the cost of completing development at IQD 21,350,000,000. Industrialists get a two-year rent exemption. In Apr 2025 the Ministerial Council for the Economy set a fixed rent of IQD 250,000 a month per half-dunum plot for years three to five. The opportunity file, which carries no date, gives IQD 750,000 a month per 1,250 m2 plot. No list of lessees was published. |  | See IND-010 for the Integrity Commission finding on the city's fence and facilities contracts. |  | all serviced plots have been leased to industrialists in accordance with applicable regulations | ["https://www.iraq-businessnews.com/2026/06/10/new-industrial-projects-launched-at-dhi-qar-industrial-city/", "https://cities.industry.gov.iq/tenders/details/5"]
IND-010 | licence or land | 2024-01-25 | Dhi Qar Industrial City: fence and facilities, built under four contracts between the Ministry of Industry and Minerals and a state company, in phases |  | A state company (not named by the Integrity Commission) |  |  |  | Dhi Qar | Dhi Qar Industrial City, Nasiriyah |  | 167,644,805,531 | IQD (spent, against an estimated cost of IQD 64,003,809,890) |  |  | The investigating judge for integrity cases in Dhi Qar asked the Federal Board of Supreme Audit to audit the payments and the ministry to open an administrative investigation, and ordered the statement of the Rafidain Bank legal representative to be taken. No later outcome was found. |  | The Integrity Commission said its Dhi Qar team, after checking the project's bank statements at Rafidain Bank, Ur branch, found IQD 167,644,805,531 paid against an estimated cost of IQD 64,003,809,890, so that the executing company received IQD 103,640,995,641 more than the original cost. Status of the unnamed company and officials: under investigation (as of 2024-01-25). |  | بيَّن تسلم الشركة المنفذة مبالغ أكثر ممَّا تستحقُّ بمقدار (103,640,995,641) مليارات دينارٍ عن التكلفة الأصليَّة للمشروع | ["https://964media.com/301064/"]
IND-011 | licence or land | 2013-12-12 | Anbar Industrial City (Hasswa al-Shamiya, Ramadi to Hit highway, junction at km 35): construction contracts and 1,847 industrial plots for small and medium industry |  | Contractors not named on the Authority's page; plot holders not named |  |  |  | Anbar | 3,000 dunums; 1,847 plots of about 1,250 m2 (40 percent of the city) |  | 56,495,838 | as printed, unit not stated (phase one contract No. 42 and its addenda) |  |  | Phase one under contract No. 42 of 12 Dec 2013 reached 31 percent; work resumed on 23 Oct 2019 after a stoppage; survey, soil tests and designs were done under contract No. 18 (printed as 425 million), listed as 100 percent complete. The first batch of plot contracts was handed to investors in Apr 2025. A ministry team inspected occupational safety in the Najaf and Anbar industrial cities in Jul 2026. No list of plot holders was found. |  | None found for this city. |  | تم تنفيذ اعمال المرحلة الاولى بموجب العقد المرقم 42 وملاحقه وبمبلغ قدره 56,495,838 في 12/12/2013 وقد بلغت نسبة الانجاز 31% | ["https://cities.industry.gov.iq/tenders/details/10", "https://cities.industry.gov.iq/news/details/72", "https://www.iraq-businessnews.com/2025/04/07/iraq-allocates-first-industrial-city-plots-in-anbar-dhi-qar/"]
IND-012 | licence or land | 2025-12-17 | Akkad Industrial City, Rashidiya, Baghdad: licence to establish and develop the first industrial city on privately owned land (light and medium industry) |  | Not named in the Industrial Cities Authority statement or in the press read |  |  |  | Baghdad | 125 dunums, privately owned | [5 empty] | On 10 Mar 2025 the Authority's deputy head, Riyadh Jassim Kadhim, said approvals had been obtained for two Baghdad cities: Rashidiya (125 dunums) and a pharmaceutical city in Yusufiya (174 dunums) to be referred to investment. The Authority's board approved the Akkad project at its second session (Iraq Business News, 1 Oct 2025), and the minister spoke of approving its referral to the private sector. The licence was handed over on 17 Dec 2025. |  | None found. Licensee not named. |  | تم تسليم اجازةانشاء وتطوير مدينة أكد الصناعية في بغداد الراشدية على مساحة ١٢٥ دونم اليوم الأربعاء الموافق ١٧ كانون الأول ٢٠٢٥ | ["https://cities.industry.gov.iq/news/details/69", "https://964media.com/523811/", "https://www.iraq-businessnews.com/2025/10/01/iraq-approves-3-new-industrial-cities/", "https://economy-news.net/content.php?id=60614"]
IND-013 | licence or land | 2025-10-01 | Babylon pharmaceutical industrial city and Babylon Gateway industrial city (food, light and medium industry), awarded at the second session of the Industrial Cities Authority board |  | Developers not named |  |  |  | Babil | 708 dunums (pharmaceutical city) and 2,000 dunums (Babylon Gateway) | [5 empty] | On 26 Oct 2025 an Authority delegation announced the official start of work in the Babylon pharmaceutical city and the Babylon city for small and medium industry, and discussed enlarging the area with the local government. |  | None found. Developers not named. |  | جرى الإعلان عن انطلاق العمل رسمياً في المدينتين الصناعيتين | ["https://www.iraq-businessnews.com/2025/10/01/iraq-approves-3-new-industrial-cities/", "https://cities.industry.gov.iq/news/details/68"]
IND-014 | licence or land | 2025-11-17 | Pharmaceutical industrial city of the State Company for Drug Industries and Medical Appliances (Samarra), to be built in partnership with a developer; the Industrial Cities Authority to issue the management and development licence |  | Developer not named; state partner: State Company for Drug Industries and Medical Appliances, Samarra |  |  |  | Not stated (Iraq Business News reports pharmaceutical industrial zones under development in Samarra and Al-Yusufiya) | 258 dunums | [5 empty] | The Cabinet decision is an exception from the company's core tasks under the Public Companies Law 22 of 1997. No developer contract was found. |  | Cabinet decision of 17 Nov 2025 (executive). No charge, court ruling, sanction or official finding was found in the sources read. |  | خول مجلس الوزراء الشركة العامة لصناعة الأدوية والمستلزمات الطبية/ سامراء، صلاحية الدخول بالمشاركة مع مطور لإنشاء مدينة دوائية صناعية على قطعة الأرض المحددة بالمساحة ( 258) دونماً | ["https://964media.com/623617/", "https://www.iraq-businessnews.com/2025/12/02/iraq-launches-45m-cancer-drug-plant-70m-vaccine-project/"]
IND-015 | licence or land | 2023-02-17 | Proposed industrial city in Habbaniyah: talks between the Industrial Cities Authority and a prospective developer |  | TRAC Development Group (South Korea; offices in Chicago, Seoul and Baghdad, per its website as cited) |  |  |  | Anbar | Not stated | [5 empty] | Only talks were reported. No licence, contract or land allocation to the company was found. |  | None. Status: not charged as of the date of writing (as of 2023-02-17). |  | held a meeting with the South Korean company TRAC Development Group to discuss establishment of an industrial city in Habbaniyah | ["https://www.iraq-businessnews.com/2023/02/17/korean-firm-discusses-building-industrial-city-in-habbaniyah/"]
IND-016 | licence or land | 2026-01-27 | Licence to establish a motorcycle and electric motorcycle factory, granted by the General Directorate for Industrial Development on a Cabinet decision |  | Babel Al-Dhahabiya (Babel Golden) Company for General Trading and the Trading and Manufacturing of Cars and Motorcycles | شركة بابل الذهبية للتجارة العامة وتجارة وتصنيع السيارات والدراجات |  |  | Not stated | Not stated | [5 empty] | No later report on the factory was found. |  | Cabinet decision of 27 Jan 2026 (executive). Status: not charged as of the date of writing (as of 2026-01-27). |  | أقرّ مجلس الوزراء قيام المديرية العامة للتنمية الصناعية، بمنح إجازة إنشاء مصنع لصناعة الدراجات النارية والكهربائية إلى شركة بابل الذهبية للتجارة العامة وتجارة وتصنيع السيارات والدراجات | ["https://964media.com/646277/", "https://964media.com/646266/", "https://www.iraq-businessnews.com/2026/01/28/iraq-to-build-new-motorcycle-factory/"]
IND-017 | licence or land | 2025-08-13 | Completion of establishment certificate for a porcelain, industrial granite and concrete products plant, granted on the basis of the environmental impact report and prior environmental approvals |  | The Italian Factory for Modern Tiles (porcelain, industrial granite and concrete products) | المصنع الإيطالي للبلاطات الحديثة لإنتاج البورسلين والكرانيت الصناعي والمنتجات الخرسانية |  |  | Baghdad | Baghdad Economic City, Nahrawan; plot area not given | [5 empty] | Approved by the Industrial Coordination Council chaired by PM al-Sudani on 13 Aug 2025. No later report was found. |  | Executive decision of the Industrial Coordination Council. Status: not charged as of the date of writing (as of 2025-08-13). |  | جرت الموافقة على قيام وزارة الصناعة والمعادن/ المديرية العامة للتنمية الصناعية بمنح المصنع الإيطالي للبلاطات الحديثة لإنتاج البورسلين والكرانيت الصناعي والمنتجات الخرسانية في مدينة بغداد الاقتصادية بالنهروان، شهادة إكمال التأسيس | ["https://964media.com/588147/"]
IND-018 | licence or land | 2021-10-17 | Establishment licence (under establishment) for a ready-mixed concrete plant, licence letter ق/ش/14113 of 17 Oct 2021 |  | Majeed Abboud ready-mixed concrete plant | معمل مجيد عبود للكونكريت الجاهز |  |  | Not stated (supporting plant for a Baghdad Municipality contract, Karkh side) | Not stated | [5 empty] | Still listed as under establishment at the time of the audit, almost four years after the licence. |  | FBSA report 19992 of 4 Aug 2025 on Baghdad Municipality contract No. 140 of 2023 (26 Mar 2023, IQD 5,678,080 thousand, direct contracting, charged to the Emergency Support for Food Security allocations) with Al-Awtar al-Fiddiya Co. for General Contracting (LLC). FBSA found that the contractor's bid listed this plant as a supporting plant, but the General Directorate for Industrial Development approvals showed it was still under establishment, with nothing to show establishment was completed, contrary to Regulation 3 of 1999 under the Industrial Investment Law 20 of 1998 (start within one year and complete within three years of the licence); the municipality's department did not inspect the plants before work began, as clause six of the contract required. FBSA recommended investigation of these observations. Status of the plant licensee: not charged as of the date of writing; status of Al-Awtar al-Fiddiya: accused by an official body (FBSA audit finding, as of 2025-08-04). |  | ان الموافقات الصادرة عن وزارة الصناعة والمعادن/ المديرية العامة للتنمية الصناعية الخاصة بمنح اجازة التأسيس اشارت الى ان تلك المعامل هي (تحت التأسيس) | ["https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026651_4169813074291734.pdf#page=476"]
IND-019 | licence or land | 2014-11-12 | Establishment licence (under establishment) for an asphalt plant, licence letter ق/13009 of 12 Nov 2014 |  | Firas Khudair Hameed asphalt plant | معمل فراس خضير حميد لإنتاج الاسفلت |  |  | Not stated (supporting plant for a Baghdad Municipality contract, Karkh side) | Not stated | [5 empty] | Still listed as under establishment at the time of the audit, more than ten years after the licence, although the regulation allows three years to complete establishment. |  | FBSA report 19992 of 4 Aug 2025 on Baghdad Municipality contract No. 140 of 2023 (26 Mar 2023, IQD 5,678,080 thousand, direct contracting, charged to the Emergency Support for Food Security allocations) with Al-Awtar al-Fiddiya Co. for General Contracting (LLC). FBSA found that the contractor's bid listed this plant as a supporting plant, but the General Directorate for Industrial Development approvals showed it was still under establishment, with nothing to show establishment was completed, contrary to Regulation 3 of 1999 under the Industrial Investment Law 20 of 1998 (start within one year and complete within three years of the licence); the municipality's department did not inspect the plants before work began, as clause six of the contract required. FBSA recommended investigation of these observations. Status of the plant licensee: not charged as of the date of writing; status of Al-Awtar al-Fiddiya: accused by an official body (FBSA audit finding, as of 2025-08-04). |  | ان الموافقات الصادرة عن وزارة الصناعة والمعادن/ المديرية العامة للتنمية الصناعية الخاصة بمنح اجازة التأسيس اشارت الى ان تلك المعامل هي (تحت التأسيس) | ["https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026651_4169813074291734.pdf#page=476"]
IND-020 | licence or land | 2020-10-07 | Approvals for two plants in Najaf, a tile (kashi) plant and an asphalt plant: bribe demanded from an investor |  | Investor not named (complainant); suspect not named |  |  |  | Najaf | Not stated |  | 3,300 thousand (as printed) | USD |  |  | The investigating judge ordered the suspect detained under Revolutionary Command Council Decision 160 of 1983 and sent to the requesting court. No verdict was found. |  | The Integrity Commission said its Baghdad investigation directorate caught the suspect in the act in Najaf as he received the bribe, after he claimed he could obtain the approvals for the two plants. Status of the unnamed suspect: arrested (as of 2020-10-07). |  | لغرض استحصال المُوافقات الخاصَّة بإنشاء معملين، أحدهما لـ(الكاشي) والثاني للاسفلت في محافظة النجف الأشرف | ["https://www.alsumaria.tv/news/localnews/360684/%D8%A7%D9%84%D9%86%D8%B2%D8%A7%D9%87%D8%A9-%D8%AA%D8%B6%D8%A8%D8%B7-%D9%85%D8%AA%D9%87%D9%85%D8%A7%D9%8B-%D9%85%D8%AA%D9%84%D8%A8%D8%B3%D8%A7%D9%8B-%D8%A8%D8%A7%D9%84%D8%B1%D8%B4%D9%88%D8%A9-%D8%B3%D8%A7%D9%88%D9%85-%D9%85%D8%B3%D8%AA%D8%AB%D9%85%D8%B1%D8%A7%D9%8B-%D9%84%D8%A7%D8%B3%D8%AA%D8%B5%D8%AF%D8%A7%D8%B1-%D8%A5%D8%AC%D8%A7%D8%B2%D8%A7%D8%AA-%D8%A5%D9%86%D8%B4%D8%A7"]
IND-021 | licence or land | 2024-08-23 | Gypsum and oxidation (oxidised asphalt) plants on Karma island and its approaches, Anbar: field audit of registered plants and their fuel |  | Plant owners not named; 58 government employees not named |  |  |  | Anbar | Not stated | [5 empty] | The suspects were referred to the Integrity Commission. No charge sheet or verdict was found. Baghdad Today, citing an unnamed Anbar official, reported an Integrity Commission investigation into IQD 896 billion of fuel supplied to about 236 gypsum plants in Anbar; this was not confirmed by an official statement in the sources read (tier D). |  | The National Security Service in Anbar, with the support team of the Supreme Anti-Corruption Committee, said a joint committee formed by judicial order with the General Directorate for Industrial Development and the Oil Products Distribution Company found only 15 of 249 plants in production, and that those involved swapped the sign boards of fictitious or demolished plants onto working ones to mislead inspection committees. Arrest and summons warrants were issued for 58 government employees. Status: charged or wanted (as of 2024-08-23). |  | ثبت بالأدلة أن من أصل (249) معملاً هنالك (15) معملاً فقط داخلاً في خط الإنتاج | ["https://964media.com/428761/", "https://baghdadtoday.news/256433-%D9%85%D9%84%D9%81-%D8%A7%D9%84%D8%B3%D8%B1%D9%82%D8%A9-%D8%A7%D9%84%D9%85%D8%B9%D9%82%D8%AF.-%D8%B4%D8%A8%D8%AD-%D8%A7%D9%84%D9%85%D8%B5%D8%A7%D9%81%D9%8A-%D9%88%D8%A7%D9%84%D9%85%D8%B9%D8%A7%D9%85%D9%84-%D8%A7%D9%84%D9%88%D9%87%D9%85%D9%8A%D8%A9-%D9%81%D9%8A-%D8%A7%D9%84%D9%83%D8%B1%D9%85%D8%A9-%D9%8A%D8%B7%D8%A7%D8%B1%D8%AF-%D9%85%D9%87%D8%B1%D8%A8%D9%8A-%D8%A7%D9%84%D9%86%D9%81%D8%B7-%D9%85%D8%AC%D8%AF%D8%AF%D9%8B%D8%A7.html"]
IND-022 | licence or land | 2023-01-22 | Waste recycling and compacting plant in Babil financed by an Industrial Bank loan in 2016, on land leased from Hilla municipality |  | Borrower not named |  |  |  | Babil | A plot owned by Hilla municipality, leased to the borrower; rent unpaid since 2017 |  | 3,200,000,000 | IQD (loan) |  |  | The borrower returned the IQD 3.2 billion to the Industrial Bank's Beirut Square branch in Baghdad after the bank asked for it. The Commission said the municipality took no step to collect the accumulated rent. No charge was reported. |  | The Integrity Commission said its investigation found the plant fictitious, with no existence on the ground. Status of the unnamed borrower: accused by an official body (as of 2023-01-22). |  | منح القرض بالمبلغ المذكور في العام 2016؛ لإنشاء معمل لتدوير وكبس النفايات في محافظة بابل الذي كشفت أنه وهمي، وليس له وجود على أرض الواقع | ["https://964media.com/56939/"]
IND-023 | licence or land | 2024-06-04 | Cabinet decision on transferring ownership of land to industrial projects (decision 24413 of 2024): the State Real Estate Directorate sells land under industrial projects to their owners, as an exception from public auction |  | Owners of industrial projects holding a completion of establishment licence from the General Directorate for Industrial Development for at least three years (not named) |  |  |  | All provinces | State land and land burdened with disposal rights on which a licensed industrial project stands, outside the basic city plans; a no-disposal mark keeps it for industrial use | [5 empty] | Amended on 6 May 2025 (rent assessed at fair rent for future cases). On 14 Oct 2025 the Cabinet exempted industrial projects on agricultural land with disposal rights that are duly licensed by Industrial Development from the State Real Estate Directorate's rent rules, so no lease contracts are signed and no rent is collected from them. On 21 Oct 2025 the Cabinet cancelled paragraph 10 of decision 24413 and allowed land under an industrial project with an investment licence to pass to the investor after 25 or 40 percent completion. The same 2024 decision told the Oil Ministry to supply industrial projects their fuel quotas as set by the Directorate's needs assessment. No list of buyers or sale prices was found. |  | Cabinet decisions (executive). No audit or allegation on sales under this decision was found. |  | تتولى وزارة المالية/ دائرة عقارات الدولة بيع الأراضي المشيدة عليها مشاريع صناعية لصاحب المشروع، الحاصل على إجازة إكمال التأسيس بموجب قانون الاستثمار الصناعي للقطاعين الخاص والمختلط رقم (20 لسنة 1998) وقت صدور هذا القرار، استثناءً من المزايدة العلنية | ["https://964media.com/381858/", "https://964media.com/548002/", "https://964media.com/610676/", "https://964media.com/613010/"]
IND-024 | licence or land | 2025-08-13 | Industrial Coordination Council decision 29 of 2025: each province to prepare and allocate 1,000 dunums for industrial projects nominated by the General Directorate for Industrial Development |  | Projects nominated by the General Directorate for Industrial Development (not named) |  |  |  | All provinces | 1,000 dunums in each province | [5 empty] | On 13 Aug 2025 the Council obliged the provinces to carry out the decision and launched the Directorate's electronic window for completion licences within 15 days. On 30 Aug 2026 PM Ali al-Zaidi, at the third session of the Industrial Coordination Council, again directed every province to allocate the 1,000 dunums. No list of nominated projects was found. |  | Executive decisions. No charge, court ruling, sanction or official finding was found in the sources read. |  | إلزام المحافظات بتنفيذ قرار مجلس التنسيق الصناعي رقم (29 لسنة 2025) بشأن تهيئة وفرز (1000) دونم لتخصيصها للمشروعات الصناعية المرشحة من المديرية العامة للتنمية الصناعية | ["https://964media.com/588147/", "https://964media.com/712355/"]
IND-025 | licence or land | 2024-08-05 | Ministerial Council for the Economy, 23rd session: an investor may not hold both an Industrial Development licence and an investment licence for the same project; an electronic database of industrial investment projects to be created |  | Not applicable (rule for all holders of industrial establishment licences) |  |  |  | All provinces | Not applicable | [5 empty] | The Council also set rules for provincial investment commissions on licensing industrial projects that already hold an establishment licence from the Directorate. No report on the platform's launch was found. |  | Executive decision. Our reading is that one project could hold both licences before Aug 2024; no count of such cases was found. |  | منع المستثمر من الجمع بين إجازتين (إجازة التنمية الصناعية واجازة الاستثمار) لنفس المشروع | ["https://964media.com/419318/"]
IND-026 | licence or land | 2025-12-31 | Accounts and contract control of the General Directorate for Industrial Development and the Industrial Cities Authority (FBSA annual report 2025, attached tables) |  | Not applicable (the licensing bodies themselves) |  |  |  | Baghdad (head offices) | Not applicable | [5 empty] | No published financial statements of the Directorate for 2018 to 2024 were found. |  | Table 4 of the FBSA 2025 annual report lists bodies that had not submitted their financial statements by 31 Dec 2025: the General Directorate for Industrial Development for 2018 to 2024 and the Industrial Cities Authority for 2022 to 2024. FBSA report 6095 of 3 Mar 2025 on the Industrial Cities Authority is listed in Table 14 (low contractual completion rates in some contracts, observation 4) and Table 17 (internal audit did not check all stages of the contract and its file, observation 3); the contracts are not named in the tables. |  | الإدارات التي لم تقدم بياناتها المالية | ["https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026651_4169813074291734.pdf#page=660", "https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026651_4169813074291734.pdf#page=661", "https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026651_4169813074291734.pdf#page=680", "https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026651_4169813074291734.pdf#page=683"]
MIC-001 | contract | 2010-04 | Karbala cement plant |  | Karbala Cement Manufacturing Ltd (KCML), a joint venture of Lafarge (France) and MerchantBridge (UK private equity group) | شركة لافارج الفرنسية | State Company for Southern Cement (now part of the State Company for Iraqi Cement) |  |  |  |  | 200,000,000 | USD (investment stated in the contract, per Alsumaria. Bloomberg, quoted by Iraq Business News, put the 2010 deal at USD 220 million) | Lease, rehabilitation and production sharing for 15 years from October 2010, as described in the IFC project summary. The investor was to raise output to about 2 million tonnes a year. Karbala provincial council said the contract required the company to generate its own electricity. |  | Lafarge took the plant over from the ministry on 6 Oct 2010. On 27 Jun 2011 Karbala provincial council decided to cut grid power to the plant, which used 15 MW of the province's 125 MW share. In November 2011 MerchantBridge gave output as 576,000 tonnes a year. IFC said it was lending USD 70 million for the rehabilitation, with USD 20 million more from Proparco (reported on 1 Jan 2013). On 22 Sep 2015 the Cabinet authorised the minister to negotiate with Lafarge on investment in the plant and to put the result to the Prime Minister. On these dates the 15 year term ran to October 2025. What followed was not found in the sources read. |  | No audit bureau or Integrity Commission finding on this contract was found. Lafarge and MerchantBridge: not charged as of the date of writing in this matter. |  | «وينص العقد المبرم بين الشركة الفرنسية والحكومة العراقية على تخصيص مئتي مليون دولار كقيمة استثمارية لمعمل اسمنت كربلاء لرفع طاقته الإنتاجية لتصل إلى نحو مليوني طن سنويا» [alsumaria.tv] ¦¦ «Karbala Cement Manufacturing Ltd (KCML) is an Iraqi company that entered in April 2010, into an agreement with the Government of Iraq for the leasing, rehabilitation and production-sharing of a state-owned cement plant in Karbala, southern Iraq for 15 years (starting October 2010).» [ewsdata.rightsindevelopment.org] ¦¦ «He said that the Lafarge was supposed to generate its own electric power according to the contract it had signed.» [iraq-businessnews.com] ¦¦ «A meeting of the Iraqi cabinet on Tuesday authorised the Minister of Industry and Minerals to negotiate with the French company Lafarge concerning investment in the Karbala cement plant» [iraq-businessnews.com] | ["https://ewsdata.rightsindevelopment.org/projects/IFC-32206/", "https://www.alsumaria.tv/news/32583/", "https://www.iraq-businessnews.com/2010/05/24/uk-company-cements-iraq-deal/", "https://www.iraq-businessnews.com/2011/06/28/karbala-cuts-power-to-cement-plant/", "https://www.iraq-businessnews.com/2011/11/24/lafarge-to-triple-cement-production-at-karbala/", "https://www.iraq-businessnews.com/2013/01/01/world-bank-to-finance-lafarge-cement-plant-in-kerbala/", "https://www.iraq-businessnews.com/2015/09/22/lafarge-in-negotiations-on-karbala-cement-plant/"]
MIC-002 | contract | 2013-06-23 | Babil cement plant |  | Two Turkish heavy industry companies named in Arabic as Anta and Orban (Latin spelling not found), and Al-Minna Contracting (Iraqi) | شركتا انتا واوربن للصناعات الثقيلة التركيتان؛ شركة المنة للمقاولات العراقية | State Company for Southern Cement (now part of the State Company for Iraqi Cement) | [6 empty] | Investment and development contract for 15 years. The ministry receives 15 percent of total output free in the first five years and 20 percent after that. The investors keep all 750 workers. The plant and its machinery return to the ministry at the end. Target: the design capacity of 220,000 tonnes a year. |  | The director-general of Southern Cement, Sinan al-Saeedi, announced the contract and said there were other investment contracts for the company's plants. Later performance of this contract was not found in the sources read. In 2020 the plant's laboratories went to another contractor under contract No. 419. |  | None found for the 2013 contract. |  | «الشركة وقعت عقدا مع شركتي انتا واوربن للصناعات الثقيلة التركيتين، اضافة الى شركة المنة للمقاولات العراقية لاستثمار وتطوير معمل اسمنت بابل» [alsumaria.tv] ¦¦ «الوزارة ستحصل على نسبة 15 % من الإنتاج الكلي للمعمل مجاناً، خلال الخمس سنوات الأولى لترتفع هذه النسبة إلى 20 %، فيما بعد وطيلة فترة التعاقد البالغة 15عاماً» [alsumaria.tv] | ["https://www.alsumaria.tv/news/78219/"]
MIC-003 | contract | 2011-06-21 | Muthanna cement plant, Samawa area (built in the 1980s, design capacity 2 million tonnes a year) |  | Partner Teknik (Turkey), with an Iraqi partner not named in the report |  | State Company for Southern Cement (now part of the State Company for Iraqi Cement) |  |  |  |  | 110,000,000 | USD (spending required of the investor) | Award of a rehabilitation contract, announced by deputy minister Adel Karim. The company takes 73 percent of production and the ministry the rest, in a 15 year contract. The company must spend about USD 110 million to reach 90 percent of design capacity within 36 months and must keep all Iraqi staff. Signing was expected within days. |  | On 28 Aug 2013 the ministry signed a contract for the same plant with a different group (next row). The sources read do not say what happened to the 2011 award. The date given here is the date of the trade report. |  | None found. A company printed as Partner Tech by the audit bureau later held the Fallujah white cement contract of 2019. The sources read do not say whether it is the same firm. |  | «Karim said the company will have a 73 per cent share of production at the plant with the remainder going to the ministry in the 15-year contract.» [cemnet.com] ¦¦ «The Turkish company, which has an Iraqi partner, needs to spend around US$110m to reach 90 per cent of its designed capacity in 36 months» [cemnet.com] | ["https://www.cemnet.com/News/story/128516/us-110m-contract-awarded-to-renovate-cement-factory-iraq.html"]
MIC-004 | contract | 2013-08-28 | Muthanna cement plant (built 1984) |  | Qimmat al-Iraq (Qemmet El-Iraq, Iraqi) and ASEC Cement (Egypt) | شركة قمة العراق (محلية)؛ شركة اسيك المصرية | State Company for Southern Cement (now part of the State Company for Iraqi Cement) | [6 empty] | Investment contract for 14 years. The investors rehabilitate the whole plant and raise output to 1.8 million tonnes a year, with a free share for Southern Cement during the term. A trade report gives a target of 1.1 million tonnes a year and a free share that reaches 540,000 tonnes a year. |  | The director-general of Southern Cement, Sinan Kadhim al-Saeedi, said this was the company's third investment contract. The plant then worked at no more than 10 percent of capacity. ASEC said the main obstacle was a power station for the plant. Later performance was not found in the sources read. |  | None found in the sources read. |  | «الشركة وقعت عقدا مع شركتي قمة العراق المحلية واسيك المصرية لاستثمار معمل سمنت المثنى من خلال تأهيله وإيصاله الى طاقته الانتاجية الكاملة» [alsumaria.tv] ¦¦ «العقد الزم الشركات الاستثمارية تأهيل المعمل بالكامل والوصول بالإنتاج الى مليون و800 الف طن سنويا على ان تخصص حصة مجانية لشركة السمنت الجنوبية خلال فترة العقد البالغة 14 عاما» [alsumaria.tv] ¦¦ «The companies involved in the project will have a free share in the product that will reach at the end to 540,000 tonnes annually» [technicalreviewmiddleeast.com] | ["https://www.alsumaria.tv/news/81719/", "https://technicalreviewmiddleeast.com/construction/buildings/iraq-seeks-investments-in-cement-sector", "https://www.worldcement.com/africa-middle-east/06092013/"]
MIC-005 | contract | 2016 | Samawa cement plant, in the centre of Muthanna province (the old plant, about 70 years old) |  | Samawa Cement Production Company (an investment group). Chairman of the plant's board: Dr Ali Aziz al-Dhalimi | شركة السماوة لإنتاج السمنت | State Company for Iraqi Cement (Southern Cement) | [6 empty] | Long contract of 25 years, as reported by Baghdad Today. The investing company signed the investment contract with the Ministry of Industry. |  | According to the chairman, the plant stopped for three years soon after the contract was signed because of problems with the ministry, and restarted in 2021 with two lines (1,500 tonnes a day of ordinary cement and 3,500 tonnes a day of resistant cement). It has 150 government employees and 350 staff hired by the investor. He said a provincial council decision to close the plant was cancelled in 2016 by the experts committee of the Prime Minister's office, under the acting industry minister. An environment engineer told the outlet that the investor does not run the kilns and uses clinker imported from Iran. Residents blame the plant's dust and smoke for respiratory disease and cancer. |  | According to the report, the Muthanna environment department decided in 2008 that the plant should move out of the city. An environment engineer, Imran Karim, said he is kept from inspecting all parts of the plant. No audit or judicial finding on the contract was found. No charge, court ruling, sanction or official finding was found in the sources read. |  | «بقي المعمل ضمن عهدة الدولة لغاية سنة 2016، ليشمل بنظام الخصخصة ويصبح تحت ادارة مجموعة استثمارية (شركة السماوة لإنتاج السمنت) بعقد طويل يمتد لـ25 سنة» [baghdadtoday.news] ¦¦ «ان المعمل توقف لثلاثة سنوات عن العمل، بعد فترة وجيزة من توقيع شركته عقد استثماره بسبب مشاكل حدثت مع وزارة الصناعة، ليعود العمل سنة 2021» [baghdadtoday.news] | ["https://baghdadtoday.news/249764-.html"]
MIC-006 | contract | 2012-11-14 | Basra iron and steel plant (opened 1976, stopped fully in 2003, more than 6,000 staff) |  | UB Holding (United Brothers Holding, Turkey) | شركة (UB Holding) التركية | State Company for Iron and Steel, Basra (Khor al-Zubair) |  |  |  |  | 700,000,000 | USD | Investment contract signed on 14 Nov 2012. UB Holding undertakes to spend USD 700 million, add new lines and raise output to 1 million tonnes a year. Rehabilitation takes three years and the contract runs 18 years. Profits are shared between the two companies, with a share for Basra province. The contractor pays the salaries of the plant's workers. At the end of the term the Turkish company gives up ownership of all the equipment it supplied to the plant. A trade report adds three stages ending in 2016, including a new 820,000 tonne rebar mill and a 1.2 million tonne direct reduced iron unit. |  | The work did not go ahead as planned. On 16 Nov 2015 minister Mohammed Sahib al-Darraji said the economic committee would choose between continuing with the investor on new terms and cancelling the contract and offering the project again. On 21 Dec 2016 acting minister Mohammed Shia al-Sudani said the plant had been stopped for years as a result of a contract with a foreign company to rehabilitate and invest it. He said a Cabinet committee had reached an understanding under which the company would rehabilitate the plant for USD 118 million and the investment would wait until the rehabilitation ended, and that this needed a Cabinet decision. That decision was not found in the sources read. The rolling mill reopened in March 2024 after 21 years (500,000 tonnes a year). The Prime Minister opened the steel plant on 14 May 2025 (600,000 tonnes a year) and his office called it a project that had been stalled for more than 20 years. The statements read do not name the firm that carried out the later rehabilitation. |  | None found. In 2012 the ministry's Inspector General, Munther Abdul Karim Majid, described the contract as a long term investment contract that would lead to partial privatisation of the plant. UB Holding: not charged as of the date of writing. |  | «إدارة الشركة وقعت اليوم عقداً مع شركة (UB Holding) التركية ستتولى بموجبه إعادة تشغيل وتطوير مصنع الحديد والصلب الواقع في ناحية خور الزبير» [alsumaria.tv] ¦¦ «أعمال التأهيل والتطوير تستغرق ثلاث سنوات، بينما حددت مدة العقد بـ18 عاماً» [alsumaria.tv] ¦¦ «اللجنة أمام خيارين، أما أن تقرر المضي في عقد تشغيل المصنع مع الشركة المستثمرة وفق شروط جديدة، أو أن تقرر إلغاء العقد المبرم مع الشركة وطرح مشروع تأهيل وتشغيل المصنع مرة أخرى للاستثمار» [alsumaria.tv] ¦¦ «مجلس الوزراء شكل لجنة للتفاوض مع الشركة، وتوصلت اللجنة الى تفاهم مع الشركة يقضي بأن تقوم بتأهيل المصنع بكلفة 118 مليون دولار، وتأجيل استثمار المصنع الى حين الانتهاء من أعمال التأهيل» [alsumaria.tv] ¦¦ «مصنع الصلب في الشركة العامة للحديد والصلب بمحافظة البصرة، بعد إعادة تأهيله، بطاقة 600 ألف طن سنوياً، وهو من المشاريع التي واجهت التوقف والتلكؤ لأكثر من 20 سنة» [964media.com] | ["https://www.alsumaria.tv/news/66448/", "https://www.alsumaria.tv/news/151951/", "https://www.alsumaria.tv/news/189732/", "https://www.iraq-businessnews.com/2013/03/02/details-of-700m-upgrade-to-basra-steel-plant/", "https://www.iraq-businessnews.com/2024/03/13/new-steel-rolling-mill-opens-in-basra/", "https://964media.com/551119/"]
MIC-007 | contract | 2012-12-20 | Nineveh drug plant (drug plant and cancer drug plant) |  | A Jordanian holding company (no fuller name in the report) | الشركة الأردنية القابضة | State Company for Drugs and Medical Appliances, Nineveh | [6 empty] | Investment contract for 18 years. The ministry receives a free share of 13 percent of output during rehabilitation and a permanent share after it. The investor rehabilitates the two plants, adds 150 kinds of medicine and keeps all staff. |  | The Inspector General, Munther Abdul Karim Majid, said the ministry would sign a second contract with the same company for the Samarra drug plant. On 8 Mar 2019 MP Alia Nassif objected to an investment contract for the Nineveh plant with a Jordanian company and asked the Prime Minister and the health minister to cancel any such contract. The outcome was not found in the sources read. |  | None found for this contract. A separate partnership contract for the Nineveh intravenous solutions plant is under investigation (next row). |  | «وقعت، اليوم، عقدا مع الشركة الأردنية القابضة لاستثمار مصنع أدوية نينوى» [alsumaria.tv] ¦¦ «مدة العقد ستستمر لمدة 18 عاما مع توفير حصة مجانية من الإنتاج للوزارة بمقدار 13% أثناء عمليات التأهيل وأخرى دائمية بعد الانتهاء من ذلك» [alsumaria.tv] | ["https://www.alsumaria.tv/news/68648/", "https://www.alsumaria.tv/news/262864/"]
MIC-008 | contract | 2023-03-12 | Intravenous solutions plant in Nineveh |  | A private company, not named by the Integrity Commission |  | State Company for Drugs and Medical Appliances, Samarra |  |  |  |  | 13,000,000 | USD | Partnership contract between the Samarra company and a company to rehabilitate the plant. The date given here is the date of the Integrity Commission statement. The contract date was not given. |  | The project was 40 percent complete at the time of the statement. |  | Integrity Commission, 12 Mar 2023: the Salahuddin integrity investigation court summoned the former director-general of the Samarra company under Penal Code Article 331 for violations in the partnership contract, against the rules, after a complaint by an MP. Status: under investigation (not named). Outcome not found. |  | «المُتَّهم ارتكب مُخالفاتٍ في عقد المُشاركة المُبرم بين الشركة العامَّة لصناعة الأدوية والمُستلزمات الطبيَّـة في سامراء مع إحدى الشركات؛ لتأهيل معمل المحاليل الوريديَّـة في محافظة نينوى، خلافاً للضوابط، لافتةً إلى أنَّ نسبة إنجاز المشروع بلغت 40%» [alsumaria.tv] ¦¦ «بخصوص وجود مُخالفاتٍ في عقدٍ بمبلغ (13,000,000) مليون دولارٍ» [alsumaria.tv] | ["https://www.alsumaria.tv/news/450095/"]
MIC-009 | contract | 2022-09-01 | New plant for sterile products in Samarra (ampoules and vials), 3,000 square metres |  | Sarh Technology Company for General Trading |  | State Company for Drugs and Medical Appliances, Samarra | [6 empty] | The company invested in the factory and carries out the project, according to the ministry statement as summarised by Iraq Business News. Shares and duration not published. The date is the date of the report. |  | Steel erection had started by September 2022. Completion was not found in the sources read. |  | None found in the sources read. |  | «The project is implemented by Sarh Technology Company for General Trading, which has invested in the factory.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2022/09/01/work-starts-at-new-pharma-plant-in-samarra/"]
MIC-010 | contract | 2026-07-01 | Production line for asthma inhalers at the Baghdad plant for medicines, appliances and medical gases |  | Private partner not named |  | State Company for Drugs and Medical Appliances, Samarra | [6 empty] | Partnership contract with the private sector. Capacity 9 million units a year and nine products. |  | Two products were completed and were being registered with the Ministry of Health in July 2026, according to the director-general, Mohammed Abdul Qader al-Naimi. |  | None found in the sources read. |  | «تشغيل خط إنتاج البخاخات الفموية (بخاخات الربو) في مصنع بغداد لإنتاج الأدوية والمستلزمات والغازات الطبية، ضمن عقد شراكة مع القطاع الخاص» [964media.com] | ["https://964media.com/694529/", "https://www.iraq-businessnews.com/2026/07/02/samarra-drug-co-begins-local-production-of-asthma-inhalers/"]
MIC-011 | contract | 2021-11-20 | Glass plant and ceramics plant in Ramadi, with seven production projects |  | A consortium of Russian companies, not named (the ministry's English summary says Federation of Russian Companies) | اتحاد شركات روسية (غير مسماة) | State Company for Glass and Refractories, Anbar |  |  |  |  | 7,305,000 | USD (contract value stated by the Integrity Commission) | Investment contract for rehabilitation, operation and production sharing. Four bids were received and a Russian company was chosen. The investor was to rehabilitate seven production projects, four in the glass plant and three in the ceramics plants, and start them in stages between five months and 25 months. All staff were to be kept and paid from revenue and by the investor. In May 2023 the ministry announced a partnership contract for seven glass and ceramic plants in Anbar with what its English summary called the Federation of Russian Companies. |  | The plants did not restart. By March 2025 the contract had been rescinded. The head of the economy and investment committee of Anbar provincial council, Hamid Dahham al-Alwani, said the ministry had won the court ruling and that the plant would be offered again. In May 2025 the state company signed an agreement with a Saudi company for a silica complex (next row). |  | Integrity Commission, 20 Nov 2023: the Anbar integrity investigation court summoned the former director-general of the State Company for Glass and Refractories under Penal Code Article 331 for violations in awarding the investment contract and its addendum. Status: under investigation (not named). Outcome not found. |  | «بعد الإعلان عن عرض المعامل للاستثمار، تم استقطاب أربعة عروض، وبعد الدراسة والتحليل والمفاضلة، رسينا باتجاه إحدى الشركات الروسية، لإعادة تأهيل وتحديث واستثمار المعامل» [shafaq.com] ¦¦ «المتهم ارتكب مُخالفاتٍ في إحالة عقد استثمار معامل الزجاج والسيراميك وملحقه المبرم مع اتحاد شركاتٍ روسيَّةٍ، مُبيّنةً أنَّ العقد الذي تبلغ قيمته (7,305,000) ملايين دولارٍ يشمل التأهيل والتشغيل والمشاركة بالإنتاج» [baghdadtoday.news] ¦¦ «وزارة الصناعة كسبت قرار المحكمة لصالحها، ما يفتح المجال أمام استثمار جديد للمعمل» [shafaq.com] | ["https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%B4%D8%B1%D9%83%D8%A9-%D8%B1%D9%88%D8%B3%D9%8A%D8%A9-%D8%AA%D8%A8%D8%A7%D8%B4%D8%B1-%D8%A8%D8%AA%D8%B4%D8%BA%D9%8A%D9%84-%D9%85%D8%B9%D8%A7%D9%85%D9%84-%D8%A7%D9%84%D8%B2%D8%AC%D8%A7%D8%AC-%D9%88%D8%A7%D9%84%D8%AD%D8%B1%D8%A7%D8%B1%D9%8A%D8%A7%D8%AA-%D9%81%D9%8A-%D8%A7%D9%84-%D9%86%D8%A8%D8%A7%D8%B1", "https://www.iraq-businessnews.com/2023/05/04/russian-firm-to-rehabilitate-7-iraqi-glass-plants/", "https://baghdadtoday.news/235972-.html", "https://www.shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%B1%D8%AF%D8%A7-%D8%B9%D9%84%D9%89-%D8%AA%D9%82%D8%B1%D9%8A%D8%B1-%D9%86%D8%B4%D8%B1%D8%AA%D9%87-%D8%B4%D9%81%D9%82-%D9%86%D9%8A%D9%88%D8%B2-%D9%85%D8%AC%D9%84%D8%B3-%D8%A7%D9%84-%D9%86%D8%A8%D8%A7%D8%B1-%D9%85%D8%B9%D9%85%D9%84-%D8%A7%D9%84%D8%B2%D8%AC%D8%A7%D8%AC-%D9%88%D8%A7%D9%84%D8%B3%D9%8A%D8%B1%D8%A7%D9%85%D9%8A%D9%83-%D9%85%D8%B7%D8%B1%D9%88%D8%AD-%D9%84%D9%84%D8%A7%D8%B3%D8%AA%D8%AB%D9%85%D8%A7%D8%B1"]
MIC-012 | contract | 2025-05-01 | Planned silica based industrial complex in Anbar (flat glass, bottles and jars, sanitary ware, tiles, insulators, sodium silicate) |  | Ajial Company (Saudi Arabia) |  | State Company for Glass and Refractories, Anbar | [6 empty] | Strategic agreement signed under the patronage of minister Khaled Battal al-Najm. Shares, value and duration not published. The date is the date of the report. |  | In November 2025 the State Company for Petrochemical Industries said it had signed a preliminary agreement with Ajial to prepare feasibility studies within three months for a new petrochemical complex and for the Nebras project. |  | None found in the sources read. |  | «signing of a strategic agreement between Iraq's State Company for Glass and Refractories and Saudi-based Ajial Company to develop the largest integrated industrial complex in the region based on silica as a core raw material.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2025/05/01/saudi-arabia-to-build-silica-based-industrial-complex-in-anbar/", "https://www.iraq-businessnews.com/2025/11/12/basra-petrochemical-company-announces-new-projects/"]
MIC-013 | contract | 2018-12-19 | Kirkuk cement plant, Laylan |  | Kirkuk Cement Company Ltd. Shareholders named in the sources: AHG Industry GmbH & Co. KG (Germany) with AHG (Middle East), and Salah Al-Din Holding. The authorised director was a German national named in Arabic as لوتس شتاخه | شركة سمنت كركوك المحدودة. الشركاء بحسب بيان السمنت العراقية: (اهاكي الالمانية)، شركة الشرق الاوسط، شركة صلاح الدين | State Company for Iraqi Cement (formerly Northern Cement) |  |  |  |  | 878,000,000 | USD (amount AHG claimed from Iraq at ICSID. Iraq's Ministry of Justice later called it a USD 1 billion case) | Rehabilitation and operation contract under the Companies Law between the state company and Kirkuk Cement Company Ltd. The contract date, the shares and the duration are not stated in the sources opened. The date given here is the date of the state company's statement that describes the contract. |  | In February 2018, according to the state company, unidentified gunmen entered the plant with a copy of a registrar's letter that transferred AHG's shares to another person. The governor of Kirkuk ordered them out and the plant was handed to the state company. On 19 Dec 2018 the state company said the German director had reported that his shares were transferred without his knowledge, on the basis of a Karrada court ruling built on a sales list for 20,000 tonnes of cement that the plant manager said was forged. It said Aryan Issam, who had held a press conference as the plant's investor, had no legal capacity. On 23 Dec 2018 plant employees demonstrated in Laylan and asked for the investment to be cancelled. AHG then filed ICSID case ARB/20/21 and claimed USD 878 million for alleged expropriation. |  | ICSID tribunal, 30 Sep 2022: the claim was dismissed, reportedly for manifest lack of legal merit. AHG applied for annulment. On 11 Mar 2025 Iraq's Ministry of Justice said the tribunal had dismissed AHG's claims. No official body accuses AHG in the sources read (not charged as of the date of writing). According to the state company's statement of 19 Dec 2018, arrest and search warrants were issued for Salah Madloul Abbas and Ramyar Fathallah Mustafa for forging the sales list, and Aryan Issam was wanted on judicial arrest warrants. Status of the three as of 19 Dec 2018: charged or wanted, as stated by the state company. Court papers were not seen and the later outcome was not found. |  | «معمل سمنت كركوك التابع الى الشركة العامة للسمنت العراقية محال بعقد تاهيل وتشغيل حسب قانون الشركات الى شركة سمنت كركوك المحدودة مديرها المفوض لوتس شتاخه الماني الجنسية وشركائه شركة الشرق الاوسط وشركة صلاح الدين وحسب العقد الموقع» [alsumaria.tv] ¦¦ «وصدرت اوامر قبض وتحري بحق المدعو صلاح مدلول عباس وراميار فتح الله مصطفى لقيامهم بتزوير قائمة البيع» [alsumaria.tv] ¦¦ «نائب المدير المفوض بشركة سمنت كركوك اريان عصام ليس له اي صفة قانونية ومطلوب القبض عليه باوامر قبض صادرة من القضاء» [alsumaria.tv] ¦¦ «AHG Industry GmbH & Co. KG was said to be claiming $878 million from the Republic of Iraq for the alleged expropriation of its cement production business.» [iraq-businessnews.com] ¦¦ «the dispute stemmed from a contract for the rehabilitation and operation of Kirkuk Cement Plant between Iraq's State Company for Cement and AHG (Middle East) and Salah Al-Din Holding» [iraq-businessnews.com] | ["https://www.alsumaria.tv/news/255525/", "https://www.alsumaria.tv/news/255921/", "https://www.iraq-businessnews.com/2022/10/13/878m-arbitration-case-against-iraqi-govt-dismissed/", "https://www.iraq-businessnews.com/2025/03/13/iraq-wins-in-1bn-arbitration-case-against-german-firm/"]
MIC-014 | contract | 2010-12-02 | Sinjar cement plant, Nineveh |  | A Turkish company, not named in the reports read |  | Northern Cement State Company (now part of the State Company for Iraqi Cement) |  |  |  |  | 100,000,000 | USD (about, planned investment) | Approval to develop the Sinjar plant and invest in it for 15 years, raising output to 1.8 million tonnes a year. In December 2008 a ministry delegation in Amman had made an agreement to rehabilitate and develop the Sinjar plant over 15 years. |  | Hussein al-Khafaji of Northern Cement reported the approval. He said the ministry had signed an agreement with the same Turkish company three months earlier to develop Northern Cement's plants in Nineveh. The later fate of the contract was not found in the sources read. |  | None found in the sources read. |  | «A Turkish company has received approval to develop the Sinjar Cement Plant and invest it for 15 years, according to a source from the Northern Cement State Company (NCSC).» [cemnet.com] ¦¦ «Another agreement has been made to rehabilitate and develop a cement factory in Sinjar over a period of 15 years» [cemnet.com] | ["https://cemnet.com/News/story/130069/turkish-company-to-develop-iraq-plant.html", "https://www.cemnet.com/News/story/135163/foreign-companies-contracted-to-renovate-plants-iraq.html"]
MIC-015 | contract | 2008-11 | Kubaisa cement plant, Hit district, Anbar |  | Cement Experts for Development and Investment (Jordan), which holds 51 percent of the joint investment in the plant. Northern Region Cement (Saudi Arabia) owned 50 percent of Cement Experts and agreed in February 2024 to sell it to AMP Global Trading (UAE). Technical support from 2009: Marubeni and Kawasaki Plant Systems (Japan) |  | State Company for Iraqi Cement | [6 empty] | Preliminary agreement signed in Amman in late November 2008 with international companies to rehabilitate and develop the plant. On 20 Dec 2009 Marubeni and Kawasaki agreed to give technical help and parts to the local firm in charge of the renovation. The state's share and the duration of the investment contract were not published in the sources read. |  | The plant was damaged and looted under ISIS. One stage reopened in early March 2021 and the state company said the plant then made about 145,000 tonnes a month, its highest output. In February 2024 Northern Region Cement told the Saudi exchange that it would sell its 50 percent of Cement Experts to AMP Global Trading for USD 55 million, a sale that also covers the 51 percent share in the Kubaisa joint investment. |  | None found in the sources read. |  | «In late November, the ministry signed a preliminary agreement with international companies in the Jordanian capital to rehabilitate and develop Kabeesa cement factory.» [cemnet.com] ¦¦ «Cement Experts for Development and Investment owns 51% of the joint investment in the Al-Kubaisa cement plant in Iraq.» [globalcement.com] ¦¦ «معمل سمنت كبيسة وصل إلى أعلى طاقة إنتاجية حققها منذ أن تم إنشاؤه، إذ أنتج قرابة الـ 145 ألف طن شهرياً» [shafaq.com] | ["https://www.cemnet.com/News/story/135163/foreign-companies-contracted-to-renovate-plants-iraq.html", "https://cemnet.com/News/story/132830/iraqi-cement-plant-renovation.html", "https://globalcement.com/news/17714-northern-cement-sells-entire-stake-in-cement-experts-for-us-55m", "https://enterpriseam.com/ksa/2024/02/14/northern-region-cement-sells-entire-stake-in-cement-experts/", "https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%A7%D9%84-%D9%86%D8%A8%D8%A7%D8%B1-%D8%A8%D8%B5%D8%AF%D8%AF-%D9%8A%D9%82%D8%A7%D9%81-%D8%A7%D9%84%D8%A7%D8%B3%D8%AA%D9%8A%D8%B1%D8%A7%D8%AF-%D9%85%D8%B9%D9%85%D9%84-%D8%B3%D9%85%D9%86%D8%AA-%D9%83%D8%A8%D9%8A%D8%B3%D8%A9-%D9%8A%D8%AD%D9%82%D9%82-%D8%B9%D9%84%D9%89-%D8%B7%D8%A7%D9%82%D8%A9-%D8%A7%D9%86%D8%AA%D8%A7%D8%AC%D9%8A%D8%A9-%D9%88%D9%8A%D9%85%D8%AA%D8%B5-%D8%A7%D9%84%D8%A8%D8%B7%D8%A7%D9%84%D8%A9"]
MIC-016 | contract | 2017-02-09 | Basra cement plant, near Umm Qasr |  | Um Qasr Northern Cement Co. Ltd (Iraq), Sarh Zamzam for Investment and Rehabilitation of Industrial Projects (Jordan), and Northern Cement Co. (Jordan), a subsidiary of Northern Region Cement Co. (Saudi Arabia). From December 2023 also Al-Diyar Al-Iraqia for Investments Company, which bought 49 percent of the Saudi group's investments in Iraq | شركة أم قصر الشمالية لصناعة الاسمنت المحدودة؛ شركة صرح زمزم للاستثمار وتأهيل المشاريع الصناعية (أردنية)؛ شركة اسمنت الشمالية (الأردن) | State Company for Iraqi Cement (Southern Cement) |  |  |  |  | 3,000,000,000 | IQD (capital of the Iraqi project company) | Contract to rehabilitate and operate the Basra cement plant and share in its production. On 9 Feb 2017 the board of Northern Cement (Jordan) approved taking 20 percent of a new Iraqi limited company, with capital of IQD 3 billion, formed to carry out the contract, and 50 percent of the Jordanian company Sarh Zamzam, formed for the same purpose. The state's share and the duration were not published in the sources read. |  | In 2023 Northern Region Cement said it owned 100 percent of Um Qasr Northern Cement, directly and indirectly, and reported revenue of USD 34.4 million and net profit of USD 1.2 million for its Iraq subsidiary in 2022. In November 2023 it signed a USD 139 million contract with KHD for a new production line in Iraq (site not stated in the reports read). In December 2023 Al-Diyar Al-Iraqia agreed to buy 49 percent of its investments in Iraq for USD 43.953 million, and the Prime Minister commended the deal. In May 2024 the ministry said the Basra plant had reached its design capacity of 600,000 tonnes a year in collaboration with the private sector. Al-Diyar Al-Iraqia is also the developer of Najaf Industrial City. |  | None found in the sources read. |  | «تأسيس شركة عراقية محدودة المسؤولية غاياتها تنفيذ عقد تأهيل و تشغيل والمشاركة في الانتاج لـ (معمل اسمنت البصرة) وذلك بنسبة (20%) من رأس مال الشركة المنوي تأسيسها في العراق» [aleqt.com] ¦¦ «NRCC agreed on the acquisition by Al-Diyar Al-Iraqia For Investments Company of 49 percent of its investments in Iraq, stating a transaction value of $43.953 million.» [iraq-businessnews.com] ¦¦ «has announced that the Basra Cement Plant has achieved its design capacity with an annual production of 600,000 tons.» [iraq-businessnews.com] | ["https://www.aleqt.com/2017/02/09/article_1134126.html", "https://en.jcement.ru/content/news/saudi-company-invests-150-million-to-establish-a-production-line-in-iraq/", "https://www.iraq-businessnews.com/2023/11/08/iraq-to-get-new-139m-cement-production-line/", "https://www.iraq-businessnews.com/2023/12/14/iraqi-saudi-firms-sign-44m-cement-partnership/", "https://www.iraq-businessnews.com/2024/05/03/basra-cement-plant-achieves-design-capacity/"]
MIC-017 | contract | 2021-07 | New Badush cement plant (also called Al-Wataniya), Nineveh |  | Not named in the ministry clarification or in the reports read for this row. |  | State Company for Iraqi Cement (Northern Cement) | [6 empty] | Referral of the plant to investment. The investor pays the salaries of daily wage workers and employees, treats the filters to cut dust, and is assessed by Northern Cement after one year. A workers' representative said the contract was signed about ten days before 21 Jul 2021. |  | About 1,200 daily wage workers protested and blocked the road to the plant on 17 Jul 2021. They said the plant made about 4,000 tonnes a day and feared dismissal. The head of Northern Cement, Ali Zaidan, said the plant had not reached a profitable output, that all ministry companies lose money and that salaries are paid from a Finance Ministry grant. |  | Nothing new here. |  | «من ضمن شروط العقد هو دفع رواتب الاجراء اليوميين والموظفين» [shafaq.com] ¦¦ «عقد الاستثمار الخاص بمعمل سمنت الوطنية وقع قبل عشرة أيام، وحظي برفض شديد بين عمال المعمل» [kirkuknow.com] | ["https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D9%85%D8%AF%D9%8A%D8%B1-%D9%85%D8%B9%D9%85%D9%84-%D8%B3%D9%85%D9%86%D8%AA-%D8%A8%D8%A7%D8%AF%D9%88%D8%B4-%D9%8A%D9%83%D8%B4%D9%81-%D8%AA%D9%81%D8%A7%D8%B5%D9%8A%D9%84-%D8%B9%D9%82%D8%AF-%D8%A7%D9%84%D8%A7%D8%B3%D8%AA%D8%AB%D9%85%D8%A7%D8%B1-%D9%88%D9%8A%D8%B5%D9%81%D9%87-%D8%A8%D9%80-%D8%A7%D9%84%D8%AE%D8%A7%D8%B3%D8%B1", "https://kirkuknow.com/ar/news/66109"]
MIC-018 | contract | 2019-03-06 | Abu Ghraib dairy plant, west of Baghdad (founded 1958) |  | A Turkish dairy company (name as printed in Arabic, Latin spelling not found) | شركة مكأكوناين التركية | State Company for Food Products | [6 empty] | Investment contract to operate the plant for 15 years. All staff keep their jobs. The investor handles production, imports raw materials and markets the products. Reported by Baghdad Today from Anadolu Agency, quoting the director-general, Mohammed Jabbar. The report describes the state company as part of the Ministry of Trade. |  | On 14 Oct 2019 the ministry still listed the contract to rehabilitate and operate the Abu Ghraib lines among contracts that would follow soon. In January 2023 the state company signed a new partnership contract for the same plants with a local company (next row). |  | None found in the sources read. |  | «شركة مكأكوناين التركية المتخصصة بصناعة الألبان ستتولى تشغيل معمل ألبان أبو غريب لمدة 15 عاماً» [baghdadtoday.news] | ["https://baghdadtoday.news/77108-.html", "https://www.alsumaria.tv/news/321574/"]
MIC-019 | contract | 2023-01-10 | Abu Ghraib dairy plants (yogurt lines Rafidain, Dijla and Furat) |  | A local company called Allied, as printed by Iraq Business News |  | State Company for Food Products | [6 empty] | Partnership contract to rehabilitate the plants, add new lines and products, and manage the existing lines and machinery. Shares and duration not published. The date is the date of the report. |  | Not found in the sources read. |  | None found in the sources read. |  | «has signing of a partnership contract with a local company called "Allied", to rehabilitate Abu Ghraib dairy factories and add new lines and products.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2023/01/10/new-contract-to-rehabilitate-abu-ghraib-dairy-factories/"]
MIC-020 | contract | 2019-09-29 | Diwaniya tyre plant: shredders used to recycle old tyres |  | An investor, not named |  | State Company for Rubber Industries and Tires | [6 empty] | Partnership contract for 12 years. The investor collects old tyres, shreds them with the plant's shredders and makes new products such as running track surface and granules for small football pitches. |  | The plant manager, Numan Mohammed, said this was the plant's only activity. He said an offer had been referred to an investor to develop the plant to 500,000 large tyres a year. In February 2018 the plant had stopped production for lack of raw materials and weak marketing. |  | None found in the sources read. |  | «عقد شراكة بين الشركة العامة للإطارات التابعة لوزارة الصناعة، وبين مستثمر لمدة 12 سنة، يقوم بجمع الإطارات القديمة ليثرمها بواسطة الثرامات الموجودة في المعمل وتدويرها إلى منتجات جديدة منها التارتان وحبيبات ملاعب الخماسي» [baghdadtoday.news] | ["https://baghdadtoday.news/97373-.html"]
MIC-021 | contract | 2026-02-21 | Integrated project for specialised rubber products (three lines, including conveyor belts) |  | Private partner not named |  | State Company for Rubber Industries and Tires | [6 empty] | Partnership contract with the private sector, announced by the director-general, Haider Nasser Dhaher. Shares and duration not published. The date is the date of the report. |  | Not found in the sources read. |  | None found in the sources read. |  | «has signed a partnership contract with the private sector to establish an integrated industrial project for specialised rubber products.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2026/02/21/iraq-launches-integrated-rubber-manufacturing-project/"]
MIC-022 | contract | 2026-02-15 | Vehicle assembly, production and marketing system (buses, pickups, saloon cars, trucks and special equipment) |  | Iraqi and Emirati companies, not named. Kia Motor (South Korea) for the assembly of Kia 2700 pickups |  | State Company for Automotive and Equipment Industry, Iskandariya (Babil) | [6 empty] | Partnership contract announced on 15 Feb 2026 by the director-general, Dana Saadallah Saeed. Shares and duration not published. Early in February 2026 the company said it had assembled 360 Kia 2700 pickups, the first batch of 1,000, in partnership with Kia Motor. |  | Not found in the sources read. |  | A separate matter: on 12 Apr 2023 the Integrity Commission said the Hilla integrity investigation court had summoned a former director-general of the company under Penal Code Article 340 for ordering the payment of IQD 219 million to a private company although it had presented forged guarantees. Status: under investigation (not named). Outcome not found. |  | «أنها وقعت عقد شراكة مع شركات عراقية وإمارتية لإنشاء منظومة صناعية متكاملة لتجميع وإنتاج وتسويق مختلف أنواع المركبات» [shafaq.com] ¦¦ «المتهم أقدم على الإيعاز وصرف مبلغ (٢١٩) مليون دينار من أموال الشركة التي يعمل فيها إلى إحدى الشركات الأهليَّة، على الرغم من تقديم الأخيرة كفالات مزورة» [alsumaria.tv] | ["https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%A7%D9%84%D8%B9%D8%B1%D8%A7%D9%82-%D9%8A%D8%A8%D8%B1%D9%85-%D8%B9%D9%82%D8%AF%D8%A7-%D9%85%D8%B9-%D8%B4%D8%B1%D9%83%D8%A7%D8%AA-%D8%A7%D9%85%D8%A7%D8%B1%D8%A7%D8%AA%D9%8A%D8%A9-%D9%88%D8%A7%D8%AE%D8%B1%D9%89-%D9%85%D8%AD%D9%84%D9%8A%D8%A9-%D9%84%D8%AA%D8%AC%D9%85%D9%8A%D8%B9-%D9%88-%D9%86%D8%AA%D8%A7%D8%AC-%D8%A7%D9%84%D8%B3%D9%8A%D8%A7%D8%B1%D8%A7%D8%AA-%D8%A8-%D9%86%D9%88%D8%A7%D8%B9%D9%87%D8%A7", "https://www.iraq-businessnews.com/2026/02/19/iraq-and-uae-sign-vehicle-assembly-partnership/", "https://www.alsumaria.tv/news/453040/"]
MIC-023 | contract | 2022-07-24 | DAP (di-ammonium phosphate) fertiliser plant |  | AAA Holding Group (UK-based, chief executive Amet Selman). In April 2025 AAA thanked two partners in the project: Jood Al-Watan for Agricultural Production and Aljanoob Islamic Bank for Investment and Finance | شركة تربل أي البريطانية | State Company for Southern Fertilizers, Basra (Khor al-Zubair) | [6 empty] | Plant built in partnership between the state company and the British company, opened by minister Manhal Aziz al-Khabbaz on 24 Jul 2022. Three production lines of European origin with capacity of 1,500 tonnes a day (500,000 tonnes a year). An annual supply contract with the Ministry of Agriculture was signed at the opening. The split of output or profit was not published. An unnamed senior source told Shafaq News in November 2022 that on the latest batch the government took 5 percent and the investor 95 percent. A former MP said in June 2026 that the contract gives the investor 96 percent and the government 4 percent. |  | In November 2022 Shafaq News quoted an unnamed senior source who said the plant only rebagged imported fertiliser. On 12 Nov 2022 minister Khaled Battal al-Najm said the Prime Minister had ordered committees to investigate what was said about the fertiliser and its test results. In July 2023 AAA said it was doubling capacity to 1 million tonnes a year. On 26 Mar 2025 the minister ordered a technical and economic review of the Southern Fertilizers partnership contracts, including the DAP plant contract. On 20 Apr 2025 AAA said it had bought a further 45 percent stake in the phosphate fertiliser project in Basra from existing stakeholders and now held full ownership. In the same statement it thanked Jood Al-Watan and Aljanoob Islamic Bank as partners. The statement does not say in terms that they were the sellers. On 24 Jun 2026 former MP Rahim al-Daraji said he had given the minister documents on the contract and that the minister later called the matter commercial competition. |  | No published result of the committees was found. The allegations come from an unnamed source and a former MP, and neither names the company. No charge or audit finding was found. AAA Holding Group: not charged as of the date of writing by any official body in the sources read. |  | «مصنع سماد الداب في الشركة العامة لصناعة الأسمدة الجنوبية في مُحافظة البصرة الأول من نوعه في البِلاد والذي تمَّ إنشاؤه بالمُشاركة مع شركة تربل أي البريطانية» [shafaq.com] ¦¦ «حصة الحكومة العراقية فيها 5% و95% تذهب للمستثمر في المصنع» [shafaq.com] ¦¦ «AAA Holding Group has successfully completed the acquisition of an additional 45% stake in the Phosphate Fertiliser Project in Basra, following the purchase of shares from existing stakeholders. With this strategic transaction, AAA Holding Group now holds full ownership of the project.» [iraq-businessnews.com] ¦¦ «We would like to express our sincere appreciation to our valued partners, Jood Al-Watan for Agricultural Production and Aljanoob Islamic Bank for Investment and Finance» [iraq-businessnews.com] ¦¦ «عقد يمنح المستثمر نسبة 96% من المشروع مقابل 4% فقط للحكومة» [alsumaria.tv] | ["https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%A8%D8%B4%D8%B1%D8%A7%D9%83%D8%A9-%D8%B9%D8%B1%D8%A7%D9%82%D9%8A%D8%A9-%D8%A8%D8%B1%D9%8A%D8%B7%D8%A7%D9%86%D9%8A%D8%A9-%D8%A7%D9%81%D8%AA%D8%AA%D8%A7%D8%AD-%D9%85%D8%B5%D9%86%D8%B9-%D9%84-%D9%86%D8%AA%D8%A7%D8%AC-%D9%86%D9%88%D8%B9-%D9%85%D9%86-%D8%A7%D9%84%D8%B3%D9%85%D8%A7%D8%AF-%D9%88%D9%84-%D9%85%D8%B1%D8%A9-%D8%A8%D8%A7%D9%84%D8%A8%D9%84%D8%A7%D8%AF", "https://shafaq.com/ar/%D9%85%D8%AC%D8%AA%D9%80%D9%85%D8%B9/%D8%A7%D9%84%D8%B3%D9%88%D8%AF%D8%A7%D9%86%D9%8A-%D9%88%D9%88%D8%B2%D9%8A%D8%B1-%D8%A7%D9%84%D8%B5%D9%86%D8%A7%D8%B9%D8%A9-%D9%8A%D8%AA%D8%A7%D8%A8%D8%B9%D8%A7%D9%86-%D9%85%D9%84%D9%81-%D9%81%D8%B3%D8%A7%D8%AF-%D9%83%D8%B4%D9%81%D8%AA%D9%87-%D8%B4%D9%81%D9%82-%D9%86%D9%8A%D9%88%D8%B2-%D9%88%D9%8A%D8%B4%D9%83%D9%84%D8%A7%D9%86-%D9%84%D8%AC%D9%86%D8%A9-%D8%AA%D8%AD%D9%82%D9%8A%D9%82", "https://www.iraq-businessnews.com/2023/07/25/capacity-to-double-at-iraqi-fertilizer-plant/", "https://www.iraq-businessnews.com/2025/03/26/industry-minister-reviews-fertiliser-production-in-basra/", "https://www.iraq-businessnews.com/2025/04/20/aaa-holding-completes-acquisition-of-phosphate-fertiliser-project/", "https://www.alsumaria.tv/news/567951/"]
MIC-024 | contract | 2024-09-12 | New urea (nitrogen fertiliser) plant in Abu al-Khasib, Basra |  | Not named in the Prime Minister's statement. In March 2025 the minister said an Iraqi company supported by global firms would lead the project |  | State Company for Southern Fertilizers, Basra |  |  |  |  | 1,300,000,000 | USD (cost stated when the foundation stone was laid in March 2025) | Partnership contract signed on 12 Sep 2024 under the Prime Minister's patronage. Capacity 1 million tonnes a year, using dry gas, in cooperation with the State Company for Southern Fertilizers. The government promised gas at subsidised prices. |  | The minister laid the foundation stone on 23 Mar 2025. Separately, KAR Electrical Power Production Trading FZE (KEPPT), led by Sheikh Mahmood Barznji, gave KBR a design contract in July 2025 for an ammonia and urea plant in Basra, and in July 2026 engaged JP Morgan to arrange financing for a USD 1.6 billion urea plant in Basra. The sources read do not say whether that plant is the Abu al-Khasib project. |  | None found in the sources read. |  | «إنشاء مصنع لإنتاج الأسمدة النيتروجينية اليوريا في قضاء أبو الخصيب بمحافظة البصرة، بطاقة إنتاجية تبلغ مليون طن سنوياً» [shafaq.com] ¦¦ «highlighting that an Iraqi company, supported by global firms, will lead the project.» [iraq-businessnews.com] ¦¦ «has engaged JP Morgan to arrange development financing for a $1.6 billion urea plant in Basra.» [iraq-businessnews.com] | ["https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%A7%D9%84%D8%AD%D9%83%D9%88%D9%85%D8%A9-%D8%A7%D9%84%D8%B9%D8%B1%D8%A7%D9%82%D9%8A%D8%A9-%D8%AA%D9%88%D9%82%D8%B9-3-%D8%B9%D9%82%D9%88%D8%AF-%D8%A7%D8%B3%D8%AA%D8%AB%D9%85%D8%A7%D8%B1%D9%8A%D8%A9-%D9%84%D9%84-%D9%86%D8%AA%D8%A7%D8%AC-%D8%A7%D9%84%D8%B5%D9%86%D8%A7%D8%B9%D9%8A-%D9%85%D8%B9-%D8%A7%D9%84%D9%82%D8%B7%D8%A7%D8%B9-%D8%A7%D9%84%D8%AE%D8%A7%D8%B5", "https://www.iraq-businessnews.com/2024/09/17/iraq-signs-3-new-private-sector-partnerships/", "https://www.iraq-businessnews.com/2025/03/25/iraq-to-restart-nitrogen-fertiliser-production-after-40-yrs/", "https://www.iraq-businessnews.com/2025/07/17/kbr-awarded-feed-contract-for-fertiliser-plant-in-basra/", "https://www.iraq-businessnews.com/2026/07/08/jp-morgan-to-arrange-financing-for-1-6bn-basra-urea-plant/"]
MIC-025 | contract | 2012-06-04 | Baiji fertiliser plant and the Salahuddin electronics company, both placed with investors |  | Two investing companies, not named |  | State Company for Northern Fertilizers (Baiji) and the Salahuddin company for electronic production | [6 empty] | Investment contracts. Terms not published in the sources read. |  | On 4 Jun 2012 the head of Salahuddin provincial council, Ammar Yousif Hammoud, met minister Ahmed al-Karbouli over late salaries at the two sites. They agreed to give the investors one month to pay and to end a contract if delays recurred. The council also asked for a share of the profits of the Baiji fertiliser plant and the Samarra drug plant. On 29 Jan 2014 a political bloc said 1,500 staff of Northern Fertilizers had gone six months without pay. |  | None found. The threat to rescind came from the provincial council. |  | «جرى الاتفاق على إعطاء مهلة شهر واحد للمستثمرين في هذين الموقعين لصرف رواتب العاملين» [alsumaria.tv] ¦¦ «العقد سيفسخ نهائيا عند وجود أي خلل أو شكوى وسيحرم المستثمر من أي فرصة أخرى» [alsumaria.tv] | ["https://www.alsumaria.tv/news/57915/", "https://www.alsumaria.tv/news/91732/"]
MIC-026 | contract | 2024-05-02 | Baiji fertiliser plant (rehabilitation and operation) and a new compound fertiliser plant in Baiji |  | ARJ Holding LLC (United Arab Emirates). The Prime Minister's statement of 12 Sep 2024 on the rehabilitation contract speaks of a Qatari company and Swiss technology and gives no name |  | State Company for Northern Fertilizers, Baiji (Salahuddin) | [6 empty] | Contract reported on 2 May 2024 to build a compound fertiliser plant with capacity of 249,000 tonnes a year (DAP and urea). Partnership contract of 12 Sep 2024 to rehabilitate and operate the Baiji fertiliser plant with capacity of 672,000 tonnes a year. Shares and duration not published. |  | Site works for the compound fertiliser plant had begun by January 2026 in partnership with ARJ Holding. The sources read do not make clear whether the two contracts have the same partner. |  | None found in the sources read. |  | «UAE-based company ARJ Holding LLC has signed a contract to establish a compound fertilizer production project in Baiji, Salah al-Din province.» [iraq-businessnews.com] ¦¦ «تأهيل وتشغيل مصنع أسمدة بيجي، بالشراكة مع شركة قطرية، والأسس التكنولوجية من شركة سويسرية رائدة في مجال الأمونيا واليوريا» [shafaq.com] | ["https://www.iraq-businessnews.com/2024/05/02/uae-company-to-build-fertilizer-plant-in-baiji/", "https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%A7%D9%84%D8%AD%D9%83%D9%88%D9%85%D8%A9-%D8%A7%D9%84%D8%B9%D8%B1%D8%A7%D9%82%D9%8A%D8%A9-%D8%AA%D9%88%D9%82%D8%B9-3-%D8%B9%D9%82%D9%88%D8%AF-%D8%A7%D8%B3%D8%AA%D8%AB%D9%85%D8%A7%D8%B1%D9%8A%D8%A9-%D9%84%D9%84-%D9%86%D8%AA%D8%A7%D8%AC-%D8%A7%D9%84%D8%B5%D9%86%D8%A7%D8%B9%D9%8A-%D9%85%D8%B9-%D8%A7%D9%84%D9%82%D8%B7%D8%A7%D8%B9-%D8%A7%D9%84%D8%AE%D8%A7%D8%B5", "https://www.iraq-businessnews.com/2026/01/26/work-begins-on-baiji-fertiliser-plant/"]
MIC-027 | contract | 2024-09-12 | Soda and chlorine plant, Babil: expansion |  | Private partner not named |  | Furat State Company for Chemical Industries, Babil | [6 empty] | Partnership contract signed on 12 Sep 2024 under the Prime Minister's patronage. Design capacity 90 tonnes a day of caustic soda and 80 tonnes a day of chlorine. The expansion adds flake soda and other chemicals. |  | Not found in the sources read. |  | None found in the sources read. |  | «ومشروع توسعة مصنع الصودا والكلور في محافظة بابل، بطاقة تصميمية 90 طناً في اليوم من الصودا كاوية، و80 طناً في ال يوم من مادة الكلور» [shafaq.com] | ["https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D8%A7%D9%84%D8%AD%D9%83%D9%88%D9%85%D8%A9-%D8%A7%D9%84%D8%B9%D8%B1%D8%A7%D9%82%D9%8A%D8%A9-%D8%AA%D9%88%D9%82%D8%B9-3-%D8%B9%D9%82%D9%88%D8%AF-%D8%A7%D8%B3%D8%AA%D8%AB%D9%85%D8%A7%D8%B1%D9%8A%D8%A9-%D9%84%D9%84-%D9%86%D8%AA%D8%A7%D8%AC-%D8%A7%D9%84%D8%B5%D9%86%D8%A7%D8%B9%D9%8A-%D9%85%D8%B9-%D8%A7%D9%84%D9%82%D8%B7%D8%A7%D8%B9-%D8%A7%D9%84%D8%AE%D8%A7%D8%B5"]
MIC-028 | contract | 2024-03-12 | Refined sulphur production line at the Mishraq 1 field |  | Rafidain Iraq General Trading and Contracting Company |  | Mishraq Sulphur State Company, Nineveh | [6 empty] | The High Committee for Reconstruction and Investment referred the rehabilitation of the line to the company. Capacity 1.5 million tonnes of refined sulphur a year. In 2026 the state company described this as its first partnership agreement, covering rehabilitation, operation and development. The date is the date of the report. |  | The ministry said the project was one of the opportunities presented at the mining investment conference of May 2023. A second partnership followed in 2026 (next row). |  | None found in the sources read. |  | «has decided to refer the project for rehabilitating the sulphur [sulfur] production line at Al-Mishraq to Rafidain Iraq General Trading and Contracting Company» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2024/03/12/iraq-approves-revival-of-sulphur-production-lines/", "https://www.iraq-businessnews.com/2026/06/01/iraqs-mishraq-sulphur-company-signs-private-sector-partnership/"]
MIC-029 | contract | 2026-06-01 | Refined sulphur project at the Al-Lazzaka 2 field |  | A private Iraqi company, not named in the company statement |  | Mishraq Sulphur State Company, Nineveh | [6 empty] | Partnership agreement after the project was offered as an investment opportunity. Initial capacity 1 million tonnes a year. The date is the date of the report. |  | Announced by the director-general, Ahmed Abdullah Rowdhan. Nothing further found. |  | None found in the sources read. |  | «has signed a partnership agreement with a private Iraqi company to develop an integrated industrial project for refined sulphur production» [iraq-businessnews.com] ¦¦ «The company statement did not give the name of the private Iraqi company involved.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2026/06/01/iraqs-mishraq-sulphur-company-signs-private-sector-partnership/"]
MIC-030 | contract | 2025-02-09 | Planned phosphate fertiliser complex, Al-Qaim, Anbar |  | A private sector company, not named in the ministry statement |  | State Company for Phosphate, Anbar | [6 empty] | Approved by the High Committee for Reconstruction and Investment on 9 Feb 2025, in partnership with a private company that, the ministry said, met the highest evaluation standards. Planned output: 1 million tonnes of DAP and 500,000 tonnes of triple superphosphate a year, with sulphuric acid, phosphoric acid and ammonia. The same meeting approved a sponge iron plant in Basra. |  | On 30 Jan 2024 the minister had asked the phosphate company's board to speed up the offer of this investment opportunity. In March 2012 Anbar council took court action against Deputy Prime Minister Hussein al-Shahristani for not approving an earlier investment proposal for phosphate and cement plants. |  | None found in the sources read. |  | «The phosphate fertilizer complex, developed in partnership with a private sector company that met the highest evaluation standards, will produce 1 million tons of DAP fertilizer annually and 500,000 tons of triple superphosphate (TSP), along with sulfuric acid, phosphoric acid, and ammonia.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2025/02/12/iraq-approves-phosphate-and-sponge-iron-projects/", "https://www.iraq-businessnews.com/2024/02/01/minister-pushes-phosphate-fertilizer-project-in-anbar/", "https://www.iraq-businessnews.com/2012/03/13/anbar-sues-shahristani-for-blocking-phosphate-plant-investment/"]
MIC-031 | contract | 2025-05-14 | Chlorine and caustic soda plant at the Basra petrochemical complex |  | Private partner not named |  | State Company for Petrochemical Industries, Basra |  |  |  |  | 130,000,000 | USD (cost stated by the Prime Minister's office) | Plant built in partnership with the private sector with membrane cell technology. Daily output: 120 tonnes of caustic soda, 106 tonnes of liquid chlorine, 185 tonnes of hydrochloric acid and 150 tonnes of sodium hypochlorite. |  | The Prime Minister launched the works on 14 May 2025. In November 2025 the director-general, Mazen Abdul Razzaq, said the partnership contract was being carried out, that a nitrogen and oxygen project had been awarded and that a hydrochloric acid plant was under negotiation. |  | None found in the sources read. |  | «مشروع مصنع البصرة لإنتاج الكلور والصودا الكاوية، بكلفة 130 مليون دولار، وطاقة إنتاجية تزيد عن 40 ألف طن سنوياً» [964media.com] ¦¦ «The plant, developed in partnership with the private sector, will feature modern, eco-friendly membrane cell technology.» [iraq-businessnews.com] | ["https://964media.com/551119/", "https://www.iraq-businessnews.com/2025/05/15/iraq-launches-major-chemical-production-project-in-basra/", "https://www.iraq-businessnews.com/2025/11/12/basra-petrochemical-company-announces-new-projects/"]
MIC-032 | contract | 2026-01-07 | Chlorine and caustic soda plant at the Basra Paper Mill complex |  | Noor al-Hilal |  | State Company for Petrochemical Industries, Basra | [6 empty] | Partnership described by the company as national. Design capacity 50 tonnes a day of caustic soda and 44 tonnes a day of chlorine, with sodium hypochlorite and hydrochloric acid. About 140 jobs. Shares and duration not published. The date is the date of the report. |  | Not found in the sources read. |  | None found in the sources read. |  | «has announced the signing of a national partnership with Noor al-Hilal to establish a new plant for the production of chlorine and caustic soda in Basra.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2026/01/07/new-chlorine-and-caustic-soda-plant-for-basra/"]
MIC-033 | contract | 2015-01-28 | Nebras (Nibras) petrochemical complex, Basra (planned) |  | Shell |  | Ministry of Industry and Minerals (State Company for Petrochemical Industries), with the Ministry of Oil |  |  |  |  | 11,000,000,000 | USD (reported value of the deal) | Deal announced by industry minister Nasser al-Issawi on 28 Jan 2015 to build a petrochemical plant in Basra, expected on line within five to six years. |  | The complex was not built. On 21 Dec 2016 acting minister Mohammed Shia al-Sudani said there was a preliminary agreement with Shell and that the Basra local government had been left out of it, which he called one cause of the delay. Shell withdrew in February 2024 after what it called an in-depth evaluation of feasibility. The Prime Minister told the two ministries to study other options and to reconsider the size of the project. In November 2025 the state company signed a preliminary agreement with Ajial Company (Saudi Arabia) for feasibility studies. |  | None found in the sources read. |  | «Shell has reportedly signed a deal with Iraq worth $11 billion (12.8 trillion Iraqi dinars) to build a petrochemicals plant in Basra.» [iraq-businessnews.com] ¦¦ «British oil and gas company Shell has withdrawn from the proposed $11-billion Nebras [Nibras] petrochemical project in Basra.» [iraq-businessnews.com] ¦¦ «A preliminary agreement has been signed with Ajial Company of Saudi Arabia to prepare feasibility studies for both projects within three months as a step towards full implementation.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2015/01/28/shell-signs-11bn-petrochemical-deal/", "https://www.alsumaria.tv/news/189732/", "https://www.iraq-businessnews.com/2024/02/17/shell-quits-nebras-petrochemical-project/", "https://www.iraq-businessnews.com/2025/11/12/basra-petrochemical-company-announces-new-projects/"]
MIC-034 | contract | 2025-07-31 | Starch and dextrin factory in Babil, and the Al-Ameen soap and detergents factory |  | Private partners not named |  | State Company for Food Products | [6 empty] | Two partnership agreements to rehabilitate and develop the plants. The first adds a dry corn mill, a bottled water line, a gelatinised starch unit and other units. The second adds soap and detergent lines. Shares and duration not published. The date is the date of the report. |  | Announced by the director-general, Haider Shwia Mazal. Nothing further found. |  | None found in the sources read. |  | «has signed two public-private partnership agreements to rehabilitate and develop its starch and dextrin factory in Babil province and the Al-Ameen soap and detergents factory.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2025/07/31/ppp-contracts-to-develop-starch-and-soap-factories-in-iraq/"]
MIC-035 | contract | 2025-09-15 | Al-Maamoun factory, Baghdad: sulfonic acid, soap, detergent powder, detergents and cosmetics lines |  | Private partner not named |  | State Company for Food Products | [6 empty] | Partnership contract to rehabilitate and operate several production lines. Shares and duration not published. The date is the date of the report. |  | Not found in the sources read. |  | None found in the sources read. |  | «has signed a partnership contract to rehabilitate and operate several production lines at the Al-Maamoun Factory» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2025/09/15/partnership-to-rehabilitate-detergents-and-cosmetics-lines/"]
MIC-036 | contract | 2026-02-12 | Imam Ali al-Hadi vegetable oil plant, Maysan |  | A Bulgarian company, not named |  | State Company for Food Products | [6 empty] | Partnership contract under which the plant produces cooking oil of the Al-Bint brand. Terms not published. The date is the date of the report. |  | The first export shipment of cooking oil went to Jordan in February 2026. |  | None found in the sources read. |  | «produced at the Imam Ali Al-Hadi plant in Maysan province, has been exported to Jordan under a partnership contract with a Bulgarian company.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2026/02/12/iraqi-starts-export-of-cooking-oil/"]
MIC-037 | contract | 2025-10-10 | Plant for xylene, solvents and improved gasoline (six production units) |  | Private partner not named |  | State Company for Mining Industries | [6 empty] | Project completed in partnership with the private sector. Output: 44 cubic metres a day of xylene, 85 of solvent blends and 470 of improved gasoline. It needs 750 cubic metres a day of naphtha. The date is the date of the report. |  | In October 2025 operation was waiting for a naphtha allocation from the Ministry of Oil, according to the director-general, Mohammed Qasim Muftin. |  | None found in the sources read. |  | «has announced the completion of a new project to produce xylene, solvents, and high-quality refined fuel, in partnership with the private sector.» [iraq-businessnews.com] | ["https://www.iraq-businessnews.com/2025/10/10/iraq-completes-xylene-and-solvent-production-project/"]
MIC-038 | contract | 2026-09-03 | Company headquarters and plant site in Karrada, Baghdad (leather industries) |  | No buyer or investor named yet |  | State Company for Textile and Leather Industries | [6 empty] | The ministry announced that it would offer the site for sale or investment and move to other sites. |  | On 3 Sep 2026 a member of Parliament's Legal Committee, Mohammed al-Khafaji, wrote to minister Mohammed Nuri and asked for the reasons and the economic case. The letter says moving the plant would cost large sums and that there is no guarantee on the use of the proceeds. |  | No finding. A parliamentary question. The letter says the decision looks like part of a pattern of giving up the ministry's land and assets, as happened with the partnership contracts. The minister: not charged as of the date of writing. |  | «تساؤلا الى وزير الصناعة والمعادن محمد نوري، حول قراره طرح مقر الشركة العامة للجلود في منطقة الكرادة للبيع او الاستثمار» [baghdadtoday.news] ¦¦ «جزء من توجه يمثل سياق خطير في وزارة الصناعة والمعادن للتفريط بأراضيها واصولها كما حدث مع عقود المشاركة المبرمة» [baghdadtoday.news] | ["https://baghdadtoday.news/305537-.html"]
MIC-039 | contract | 2025-04-08 | Land belonging to the spinning plant |  | An investor, not named |  | Spinning and weaving plant in Nineveh (State Company for Textile and Leather Industries) | [6 empty] | According to plant workers interviewed by Alsumaria, an investor obtained land belonging to the spinning plant in order to build a residential complex. Area, licence and price were not given. |  | Workers said they could not afford homes in the complex. On 16 Sep 2025 the Cabinet approved an investment licence for a residential complex on 932 dunums of another ministry company in Mosul. |  | None found. A media report of workers' statements. |  | «تفاجأ عمال وموظفو الغزل والنسيج بمحافظة نينوى من تمكين احد المستثمرين للحصول على ارض تابعة لمعمل الغزول ليحولها الى مجمع سكني يعجز العاملون عن التملك فيه» [alsumaria.tv] | ["https://www.alsumaria.tv/news/521800/"]
MIC-040 | contract | 2021-12-02 | Land in front of the Nasiriyah plant |  | An investor, not named |  | State Company for Textile and Leather Industries, Dhi Qar (Nasiriyah textile plant) | [6 empty] | According to a document published by Alsumaria, the ministry's deputy for planning confirmed that the land in front of the plant should be handed to the investor because it belongs to Nasiriyah municipality, that the plant fence should be moved back and that the investor should pay for moving it. |  | The plant's director, Kadhim Mohammed Jaber al-Awadi, took action against the investor, who had built a wall in front of the plant, and cited ministry legal department letter 36237 of 1 Sep 2021 on removing the wall. |  | None found. The director is named as the signer of the document (not charged as of the date of writing). |  | «حيث اكد وكيل التخطيط بخصوص تسلم الارض الواقعة امام المصنع الى المستثمر كونها عائدة الى بلدية الناصرية وحسب المخاطبات بهذا الخصوص على ان يتم ازالة سياج المعمل الى الخلف ويتحمل المستثمر تكاليف النقل وتركيب السياج بدون اضرار» [alsumaria.tv] | ["https://www.alsumaria.tv/news/404893/"]
MIC-041 | contract | 2012-03-07 | Industrial city in Nahrawan, south of Baghdad |  | A local company supported by a Turkish company, neither named |  | Not a ministry company. Licence granted by the Baghdad Investment Commission |  |  |  |  | 232,000,000 | USD (project cost) | Investment licence. Area 2,000 dunums. The city was to gather Baghdad's industrial areas and to include a customs office, banks and warehouses. |  | Announced by the head of the commission. The sources do not say whether it is the same site. |  | None found for this licence. |  | «الهيئة منحت إجازة استثمارية لإنشاء مدينة صناعية في النهروان، جنوب بغداد» [alsumaria.tv] ¦¦ «سينفذ من قبل شركة محلية تساندها شركة تركية لإنجاز المراحل الأولى منه» [alsumaria.tv] | ["https://www.alsumaria.tv/news/53107/"]
MIC-042 | contract | 2013-09-12 | Advanced industrial zone in Kirkuk (location given as north of the city in 2013 and on the Laylan road in 2015) |  | Kirkuk United Company (named as executing company in the 2015 report) | شركة كركوك المتحدة | Not a ministry company. Provincial investment project in Kirkuk |  |  |  |  | 250,000,000 | USD (project cost) | Investment project on about 950 dunums, with more than 5,000 units (shops, workshops, plants, yards and services). |  | The foundation stone was laid on 12 Sep 2013. On 15 Jun 2015 the governor of Kirkuk visited and said he hoped for completion within a year to a year and a half. Completion was not found in the sources read. |  | None found in the sources read. |  | «أكدت الشركة المنفذة أن المشروع ينفذ على مساحة تبلغ نحو 950 دونماً وبكلفة 250 مليون دولار» [alsumaria.tv] ¦¦ «مشروع صناعي استثماري في العراق وتنفذه شركة كركوك المتحدة» [shafaq.com] | ["https://www.alsumaria.tv/news/82566/", "https://shafaq.com/ar/%D8%A7%D9%82%D8%AA%D8%B5%D9%80%D8%A7%D8%AF/%D9%81%D9%8A-%D9%83%D8%B1%D9%83%D9%88%D9%83-%D8%A3%D8%B6%D8%AE%D9%85-%D9%85%D8%AF%D9%8A%D9%86%D8%A9-%D8%B5%D9%86%D8%A7%D8%B9%D9%8A%D8%A9-%D9%85%D8%AA%D8%B7%D9%88%D8%B1%D8%A9-%D8%AA%D8%B1%D9%89-%D8%A7%D9%84%D9%86%D9%88%D8%B1-%D9%81%D9%8A-%D8%A7%D9%82%D9%84-%D9%85%D9%86-%D8%B9%D8%A7%D9%85%D9%8A%D9%86"]
MIC-043 | contract | 2021-04-17 | Partnership contracts rescinded by the ministry |  | Owners of several companies, not named |  | Several ministry companies (not listed in the report) | [6 empty] | Partnership contracts for which the owners say they paid large sums. Number and subject not given. |  | On 17 Apr 2021 the owners asked Prime Minister Mustafa al-Kadhimi to restore their contracts. They said the industry minister, the deputy for planning and the investment department were behind the rescission and that it caused them large losses. |  | None. A claim by the company owners, reported by Alsumaria. |  | «وزارة الصناعة أقدمت على فسخ عقودنا والتي كانت مشاركة وهي حقوق دفعنا من اجلها أموال كبيرة» [alsumaria.tv] | ["https://www.alsumaria.tv/news/379545/"]
MIC-044 | contract | 2026-09-14 | Government fertiliser production line at Khor al-Zubair |  | Not named in the reports read. |  | State Company for Southern Fertilizers, Basra (Khor al-Zubair) | [6 empty] | Plan to turn the government line into an investment opportunity. A staff representative said investment leaves the state 20 percent of output and gives most of the return to the investor. |  | Staff protested on 14 Sep 2026 and again on 23 Sep 2026 and stopped work. They asked for the plant to be started, for the directors-general to be removed after an ammonia leak, and for the line not to be signed over. |  | None found. The figure of 20 percent is the protesters' statement. |  | «وقفتنا الاحتجاجية ضد تحويل الخط الحكومي إلى استثماري، خصوصاً أن الاستثمار يتيح للدولة 20% فقط من الإنتاج بينما أغلب الريع يذهب للمستثمر» [shafaq.com] ¦¦ «رفضهم القاطع لقرار تحويل خطوط الإنتاج إلى الاستثمار» [964media.com] | ["https://shafaq.com/ar/%D9%85%D8%AC%D8%AA%D9%80%D9%85%D8%B9/%D8%AA%D8%AD%D8%B0%D9%8A%D8%B1-%D9%85%D9%86-%D8%AA%D8%B3%D8%B1%D9%8A%D8%AD-%D8%A7%D9%84%D8%B9%D9%85%D8%A7%D9%84-%D9%85%D9%88%D8%B8%D9%81%D9%88-%D8%B3%D9%85%D8%AF%D8%A9-%D8%A7%D9%84%D8%A8%D8%B5%D8%B1%D8%A9-%D9%8A%D8%AD%D8%AA%D8%AC%D9%88%D9%86-%D8%B5%D9%88%D8%B1-%D9%81%D9%8A%D8%AF%D9%8A%D9%88", "https://964media.com/719363/"]
MIC-045 | contract | 2019-10-14 | 36 investment projects and contracts signed in 2019, including the Nawra lime plant in Karbala, the paper bag plant at the Rafidain cement plant, the Fallujah white cement plant and the Kufa paper bag plant |  | Not named in the ministry statement. |  | State Company for Iraqi Cement, Al-Zawraa State Company, Al-Faris State Company and others | [6 empty] | Partnership and investment contracts. The ministry said its companies had more than 190 investment opportunities on offer. |  | The statement said contracts for the Abu Ghraib dairy lines, the dried milk plant, carton boxes and military textile products would follow soon. |  |  |  | «هذه العقود شملت عقد انتاج الغازات الطبية والصناعية ومشروع زيادة الطاقة الانتاجية لمصنع الفلاتر في شركة الزوراء العامة وعقود استثمار معمل النورة في محافظة كربلاء المقدسة ومعمل الأكياس الورقية في معمل سمنت الرافدين ومعمل سمنت الفلوجة الأبيض ومعمل الأكياس الورقية في الكوفة والتابعة جميعها إلى الشركة العامة للسمنت العراقية» [alsumaria.tv] | ["https://www.alsumaria.tv/news/321574/"]
MIC-046 | contract | 2025-10-18 | Plants that the workers' union federation says are being sold or privatised: the Fattah Pasha plant in Kadhimiya, the Cotton plant, the State Company for Petrochemical Industries and Ibn Majid State Company |  | No buyer named |  | State companies for leather and wool industries and for petrochemical industries, Ibn Majid State Company and others | [6 empty] | No contract published. The federation of workers' unions says the ministry is selling and privatising companies on the ground that they lose money and is retiring staff against their will. |  | The federation asked the government to stop all privatisation decisions and forced retirements. |  | None. A statement by the Federation of Workers' Unions of Iraq (اتحاد نقابات عمال العراق). |  | «من بينها مصانع ومعامل الشركة العامة للصناعات الجلدية والصوفية (مصنع فتاح باشا في الكاظمية) ومصنع القطنية، والشركة العامة للصناعات البتروكيمياوية، وشركة ابن ماجد العامة وغيرها بذريعة أنها خاسرة» [shafaq.com] | ["https://shafaq.com/ar/%D9%85%D8%AC%D8%AA%D9%80%D9%85%D8%B9/%D9%86%D9%82%D8%A7%D8%A8%D8%A7%D8%AA-%D8%A7%D9%84%D8%B9%D8%B1%D8%A7%D9%82-%D8%AA%D9%87%D8%A7%D8%AC%D9%85-%D8%AE%D8%B5%D8%AE%D8%B5%D8%A9-%D9%88%D8%A8%D9%8A%D8%B9-%D8%A7%D9%84%D8%B4%D8%B1%D9%83%D8%A7%D8%AA-%D8%A7%D9%84%D8%B9%D8%A7%D9%85%D8%A9-%D8%AA%D9%81%D9%83%D9%8A%D9%83-%D9%84%D9%84%D9%82%D8%B7%D8%A7%D8%B9-%D8%A7%D9%84%D8%B5%D9%86%D8%A7%D8%B9%D9%8A-%D8%A7%D9%84%D8%B9%D8%B1%D8%A7%D9%82%D9%8A"]

## About this file
Register: Ministry of Industry projects and contracts
Industrial cities, land allocations and partnership contracts for state factories, from official statements and audit reports. Being listed records a project, not an allegation.
Rows | 72
Years covered | 2008 to 2026
Built | 2026-10-12T01:13Z
Built from | The research datasets behind this site.
Rules applied | {}
Notes | Industrial cities, land allocations and partnership contracts for state factories. The ministry publishes no register of its licences or contracts, so the list is not complete. A row records a project, not an allegation.
Column | Type | Filled | Example | Meaning
id | text | 100% | IND-001 | ID. (auto)
kind | text | 100% | licence or land | Type of CBI record: memo (committee minutes), bulletin (daily sale bulletin) or single (one-day bulletin).
date | text | 100% | 2021-12-27 | Date (YYYY-MM-DD).
project_en | text | 100% | Karbala Industrial City: development contract No. 4 of 2021 | Project en. (auto)
project_ar | text | 0% |  | Project ar. (auto)
licensee_en | text | 100% | Al-Yusra Co. for General Contracting, Energy Projects and In | Licensee en. (auto)
licensee_ar | text | 31% | شركة اليسرة للمقاولات العامة ومشاريع الطاقة والتطوير الصناعي | Licensee ar. (auto)
state_company_en | text | 64% | State Company for Southern Cement (now part of the State Com | State company en. (auto)
state_company_ar | text | 0% |  | State company ar. (auto)
province | text | 36% | Karbala | Province. (auto)
land_en | text | 36% | 5,300 dunums allocated by the governorate through its land a | Land en. (auto)
land_ar | text | 0% |  | Land ar. (auto)
value | text | 29% | 2,000,000,000 | The figure.
currency | text | 29% | USD | Currency. (auto)
terms_en | text | 64% | Lease, rehabilitation and production sharing for 15 years fr | Terms en. (auto)
terms_ar | text | 0% |  | Terms ar. (auto)
follow_up_en | text | 100% | Minister Manhal al-Khabbaz announced on 30 Aug 2021 that the | Follow up en. (auto)
follow_up_ar | text | 0% |  | Follow up ar. (auto)
official_findings_en | text | 99% | FBSA report 20706 of 12 Aug 2025 found no convincing reasons | Official findings en. (auto)
official_findings_ar | text | 0% |  | Official findings ar. (auto)
quote | text | 100% | تمت احالة عقد إنشاء و تطوير مدينة صناعية في كربلاء بمساحة خم | Exact words from the source.
source_urls | text | 100% | ["https://storage.fbsa.gov.iq/2026/07/22/2026_07_22_12493026 | Source urls. (auto)
Terms used in this file | What they mean
arrest_warrant_or_charged | Charged or wanted under an arrest warrant; not convicted. | توجيه تهمة أو صدور أمر قبض، دون حكم إدانة.
arrested_or_detained | Arrested or held; not convicted. | اعتقال أو احتجاز، دون حكم إدانة.
under_investigation | Named as under investigation by an official body; not charged. | تحقيق أعلنته جهة رسمية، دون توجيه تهمة.
accused_by_official | Accused by an official body or office holder; not charged. | اتهام من جهة رسمية أو مسؤول، دون توجيه تهمة.
not_charged | Not charged as of the date of writing: named (for example as an office holder, bank owner or licence holder) with no charge, conviction, sanction or official finding. | لم تُوجَّه تهمة حتى تاريخ الكتابة: ورد الاسم (بصفة صاحب منصب أو مالك مصرف أو صاحب إجازة مثلاً) دون تهمة أو حكم أو إدراج في عقوبات أو قرار رسمي.